Warwick District Council

Local Development Scheme

March 2018

What is a Local Development Scheme?

1.1	This Local Development Scheme (LDS) has been prepared to give the local community and all interested parties information on:

- the current planning policies that are being used for deciding applications within Warwick District; and,

- the programme for reviewing these policies.

1.2	The Council is required to produce a LDS under the terms of the Planning & Compulsory Purchase Act 2004. The LDS is a three-year programme of work and is reviewed regularly.

  - The Government is committed to seeing LDS’s implemented and in particular to ensure the milestones set out are achieved. The Council will ensure that these targets are met through good project management and annual monitoring.

Warwick District’s Local Development Scheme

  - Development Services within the Council has prepared this LDS. The overall project manager is the Head of Development Services. Day to day management of the LDS will be by Business Manager, Policy & Development. In producing this LDS, the Council is committed to the following:

- to make the LDS as clear as possible to understand; and,

- to publish the LDS on the Council’s web site.

1.5	There are a number of commitments within the Local Plan (2011-2029) to review 		and/or update a variety of Development Planning Documents (DPD) and 	Supplementary Planning Documents (SPD), and these are detailed in Appendix 1.  	These commitments are due over the life of the Plan, and will therefore the LDF 	needs to prioritise which to bring forward first, along with bringing forward documents 	that arise through other need.  The priorities over the next 3 years (i.e.2018-2021) 	are:

| Title | Details | Delivery |
| --- | --- | --- |
| Canalside DPD | Identify areas for regeneration and areas for protection and to set out a framework for development. (It should be noted that the council is currently seeking to designate the canal network across Warwick District as a conservation area. This work is brought forward in a separate process to, but will be aligned with, this DPD.) | Adoption Q3 2019 |
| Leamington Town Centre Area Action Plan | Sets out the planning framework for Leamington Town Centre including identifying areas for changes of use where appropriate. (It should be noted that the Council has now appointed a regeneration partner to bring forward proposals for a Creative Quarter in Leamington town centre. As part of this work the Council and its partner will be producing a “masterplan”. The Council will review the relationship between this “masterplan” and an Area Action Plan and will update the LDS to clarify the extent and scope of any Area Action Plan if required. Furthermore, there has been substantive work conducted on a Vision of Leamington Town Centre and any future decisions regarding the AAP should pay due regard to this work.) | Adoption Q3 2020 |
| Residential Design Guide SPD | Sets out design standards for residential developments of all sizes throughout the District (note that this may be supplemented by major site-specific design guidance) | Adoption Q3 2018 |
| Parking Standards SPD | Sets out parking standards for residential, commercial and other developments | Adoption Q3 2018 |
| Affordable Housing SPD | Details the requirements to meet the affordable housing needs, including housing and tenancy mixes | Adoption Q3 2019 |
| Self Build SPD | Sets out guidance for the provision of self build and custom build plots and how the authority intends to ensure the meeting of the required volume of plots | Adoption Q3 2019 |
| East of Kenilworth Development Brief SPD | Site-specific development guidance for the major housing site allocations on the East of Kenilworth | Adoption Q1 2019 |
| Purpose Build Student Accommodation SPD | Sets out the relevant policies for the development of purpose built student accommodation in the District | Adoption Q1 2019 |
| Open Space SPD | Sets out the requirements for the provision of open space within developments | Adoption Q1 2019 |
| Air Quality SPD | A sub-regionally produced SPD that will set out the requirements with relation to Air Quality issues | Adoption Q4 2018 |
| East of Whitnash Development Brief SPD | Site-specific development guidance for the major housing site allocation on the East of Whitnash/South of Sydenham. | Adoption Q3 2019 |

The anticipated delivery plan for each of these priorities can be found in Appendix 2.

Existing Plans

2.1	This section provides an overview of the planning documents that cover Warwick District at the present time, including those prepared by other planning authorities.

Adopted Plans

2.2	The Warwick District Local Plan 2011-2029 was adopted by Warwick District Council 	in 2017 and is the principal document guiding planning decisions in the District.

2.3 	Warwickshire County Council is responsible for producing minerals and waste plans. 	These are specific topic-based Development Plan Documents (DPD) that relate to 	minerals extraction and dealing with waste development including the use of land for 	landfill and incineration. More information about these can be found at 	https://www.warwickshire.gov.uk/mwds.

Neighbourhood Plans

2.4	Neighbourhood Plans are brought forward by local Qualifying Bodies, often Town and Parish Councils.  These Plans add further local emphasis to the strategic policies of the adopted Local Plan.  Following an independent Examination, Neighbourhood Plans undergo a local referendum to gauge public support.  If supported the plan is ‘made’ is used alongside the Local Plan and other relevant DPD/SPDs in determining planning applications.  An up-to-date record of ‘made’ Neighbourhood Plans is maintained on our website [weblink].

Authority’s Monitoring Report (AMR)

2.5	The Council is required to monitor both the implementation of the LDS and the extent to which its planning policies are being implemented. For the purposes of this report, the policies of the adopted Warwick District Local Plan (2011-2029) are monitored.

2.6	It should be noted that the AMR is not a Local Development Document (LDD) and therefore is not included within the following workplans. The AMR will, however, be included within the LDF and be published on our website.

Political Management of the Local Development Framework

2.7	The Council’s decision making arrangements are as follows.

| Document | To include | To be approved by |
| --- | --- | --- |
| All Development Planning Documents | Local Plan and all other DPDs that are subject to full public examination as required by the Act. | Full Council following a recommendation by Executive. |
| Statement of Community Involvement |  | Executive |
| Local Development Scheme |  | Executive |
| Supplementary Planning Documents | Supplementary guidance, development briefs and other documents identified in this and future LDSs as SPD. | Executive |
| Annual Monitoring Report |  | Executive |

Contact details

2.10	For more information about any of the matters raised in this Local Development Scheme please contact:-

Policy & Development Team,

Development Services

Warwick District Council

PO Box 2178, Riverside House

Milverton Hill,

Royal Leamington Spa

CV32 5QH

Tel:  01926 456017

Email:  planningpolicy@warwickdc.gov.uk

2.11	This document, together with all other Local Development Documents produced by Warwick District Council will be made available on the Council’s website.

Appendix 1: Local Development Document commitments

This commitments made within the Local Plan 2011-2029 form the basis of this table, with additional documents added as such requirements develop.

| Document Title | Status | Role and contents | Coverage | Proposed Timetable |
| --- | --- | --- | --- | --- |
| 1. Leamington Town Centre Area Action Plan | DPD | Sets out the planning framework for Leamington Town Centre including identifying areas for changes of use where appropriate | Leamington Town Centre | Adoption – Q1 2020 |
| 2. Canalside Development Plan | DPD | Identify areas for regeneration and areas for protection and to set out a framework for development | The District’s canal network and immediate environs | Adoption – Q3 2019 |
| 3. Gypsy and Traveller Site Allocation Plan | DPD | Identifies sites to provide for housing needs of Gypsy and Traveller Community | District-wide | tbc |
| 4. Parking Standards | SPD | Sets out parking standards for residential, commercial and other developments | District-wide | Adoption – Q3 2017 |
| 5. Residential Design Guide | SPD | Sets out design standards for residential developments of all sizes throughout the District (note that this may be supplemented by major site-specific design guidance) | District-wide | Adoption – Q3 2017 |
| 6. Affordable Housing | SPD | Details the requirements to meet the affordable housing needs, including housing and tenancy mixes | District-wide | Adoption – Q3 2019 |
| 7. Sustainable Buildings | SPD | Sets out further detail on suitable adaption methods in order to plan for climate change | District-wide | tbc |
| 8. Open Space | SPD | Sets out the requirements for the provision of open space within developments | District-wide | Adoption – Q1 2019 |
| 9. Health Impacts | SPD | tbc | District-wide | tbc |
| 10. Self Build | SPD | Sets out guidance for the provision of self build and custom build plots and how the authority intends to ensure the meeting of the required volume of plots | District-wide | Adoption – Q1 2019 |
| 11. East of Kenilworth Development Brief | SPD | Site-specific development guidance for the major housing sites on the East of Kenilworth | East of Kenilworth | Adoption – Q1 2019 |
| 12. Purpose Build Student Accommodation | SPD | Sets out the relevant policies for the development of purpose built student accommodation in the District | District-wide | Adoption – Q1 2019 |
| 13. Whitnash East/South of Sydenham Development Brief | SPD | Site-specific development guidance for the major housing sites in Whitnash East/South of Sydenahm | Whitnash East/South of Sydenham | Adoption - Q3 2019 |
| 14. Air Quality (Coventry & Warwickshire) | SPD | Joint-working SPD covering the sub-region that will set out the requirements relating to Air Quality | District-wide | Adoption – Q4 2018 |

Appendix 2: Delivery Plan

| Year | 2018 | 2019 | 2020 |
| --- | --- | --- | --- |
| Quarter | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Canalside DPD |  |  |  |  | C | S |  | A |  |  |  |  |
| Leamington TC AAP |  |  |  |  |  |  |  |  | C | S |  | A |
| Residential Design Guide SPD |  | C | A |  |  |  |  |  |  |  |  |  |
| Parking Standards SPD |  | C | A |  |  |  |  |  |  |  |  |  |
| Affordable Housing SPD |  |  |  |  |  | C | A |  |  |  |  |  |
| Self Build SPD |  |  |  | C | A |  |  |  |  |  |  |  |
| East of Kenilworth Development Brief SPD |  |  |  | C | A |  |  |  |  |  |  |  |
| Purpose Build Student Accommodation SPD |  |  |  | C | A |  |  |  |  |  |  |  |
| Open Space SPD |  |  |  | C | A |  |  |  |  |  |  |  |
| Air Quality SPD |  |  | C | A |  |  |  |  |  |  |  |  |
| East of Whitnash Development Brief SPD |  |  |  |  |  | C | A |  |  |  |  |  |

| Key |  |  |
| --- | --- | --- |
| Quarters |  |  |
| 1 = January – March | 2 = April – June |  |
| 3 = July – September | 4 = October – December |  |
| Production |  |  |
| Publication |  |  |
| D = Draft Completed C = Consultation S = Submission |  |  |
| A = Adoption |  |