## S106 spreadsheet
Ward | Application number | Description of Development | Planning decision date | Development address | Description of contribution/requirement | Trigger | Conditions | Code | Paid/Delivered | Amount invoiced and received | Status | Amount | Spend by | Original amount received | Remaining balance | Responsible authority
Leamington Willes | W/03/0393 | Residential development to provide affordable housing: Amendment to W/98/0166 to increase the no. of dwellings to 49 | 2004-04-14 | St Fremund Way/Chesterton Drive | Transfer of land for open space | 100% occupation |  | Open Space |  |  | February 2016: Discussions ongoing re open space transfer. Conclusion anticipated shortly. |  |  |  |  | WDC Leisure
Kenilworth Park Hill | W/05/0262 | Outline permission for residential development | 2007-04-02 | Land at Dalehouse Lane, Kenilworth | Education contribution to be paid in accordance with the formula in the agreement. | 100% on occupation of the 1st dwelling |  | Education | Received |  | February 2016: £76,237 for Primary and £ 93,179 for Secondary received: to be spent upon identifiction of appropriate solution for Kenilworth. | In accordance with formula |  | 169416 | 0 | WCC Education
Warwick South | W/05/0962 | Alterations and extensions including mezzanine floor. | 2008-02-20 | Tesco Store, Emscote Road, Warwick | Mova contribution | Prior to implementation | Towards the upgrade of the Coventry Road/St Johns traffic signal controlled junction or towards other junction capacity improvements along the Emscote Road corridor; | Highways | Y | 75000 | February 2016:It is proposed to upgrade the traffic signal junction on Emscote Road/Tescos which is included in the highways capital programme. | 75000 | 2016-03-27 |  | 74593 | WCC Highways
Warwick South | W/05/0962 | Alterations and extensions including mezzanine floor. | 2008-02-20 | Tesco Store, Emscote Road, Warwick | Cycle Lanes contribution | Within 10 working days of implementation. | towards the completion of the Emscote Road cycle lane between the junction of the Tesco Store with Emscote Road and Portobello Bridge; | Highways | Y | 75000 | February 2016:To be developed with match funding during 2015/16. | 75000 | 2016-03-27 |  | 75000 | WCC Highways
Warwick North | W/05/1210 | Erection of a two storey block of 6 apartments | 2005-09-26 | 51 Hill Street, Warwick, CV34 5NX | Open Space Commuted Sum | 100% on Commencement |  | Open Space |  |  | February 2016:Contribution received in 2014 but not yet spent | 5496 |  |  |  | WDC Leisure
Kenilworth Park Hill | W/06/0125 | Residential development: 33 units | 2006-09-25 | Hillcrest Garage, Coventry Road, Kenilworth | Primary Education Contribution | 100% on occupation of the 1st dwelling. |  | Education | Y |  | February 2016:Received: to be spent upon identifiction of appropriate solution for Kenilworth. | 51340 |  | 55341 | 0 | WCC Education
Kenilworth Park Hill | W/06/0125 | Residential development: 33 units | 2006-09-25 | Hillcrest Garage, Coventry Road, Kenilworth | Secondary Education Contribution | 100% on occupation of the 1st dwelling. |  | Education | Y |  | February 2016:Received: to be spent upon identifiction of appropriate solution for Kenilworth. | 62760 |  | 67650 | 0 | WCC Education
Warwick South | W/09/0144 | Erection of extensions to the super store to provide additional sales and bulk floorspace, a dot com facility, and associated works.(Amended scheme to planning application reference W05/0962). | 2010-11-24 | Tesco Supermarket, Emscote Road, Warwick, CV34 5QL | Cycleway Contribution | Within 10 days of implementation |  | Highways |  |  | February 2016:Received. Scheme proposed for 16/17 and currently being planned. | 75000 |  |  |  | WCC Highways
Warwick South | W/09/0144 | Erection of extensions to the super store to provide additional sales and bulk floorspace, a dot com facility, and associated works.(Amended scheme to planning application reference W05/0962). | 2010-11-24 | Tesco Supermarket, Emscote Road, Warwick, CV34 5QL | CCTV Contribution (to be paid to WCC) | Within 10 days of implementation |  | CCTV |  |  | February 2016:Received. Scheme proposed for 16/17 and currently being planned. | 10000 |  |  |  | WCC
Clarendon | W/10/0975 | Conversion of buildings to student accommodation | 2011-03-07 | 46-48 Bedford Street, Leamington | Open space contribution | On commencement of the development |  | Open Space |  |  | February 2016:Contribution received but not yet spent. Spend end of 2019 at the latest | 5652 |  |  |  | WDC Leisure
Clarendon | W/10/1370 | 3 storey building to form retail units and student accommodation | 2012-04-10 | 13-17 Kenilworth Street, Leamington Spa | Open space contribution | 100% prior to commencement |  | Open Space |  |  | Scheme in progress: contribution being sought by WDC. | 8164 |  |  |  | WDC Leisure
Leamington Milverton | W/10/1664 | Removal of roof and top section of walls of single storey part of existing building and conversion of remaining two storey building into a dwelling; re-roofing of rear roof slope with slate; installation of new windows and doors; installation of solar panels and rooflights; and retention of existing walls to create front courtyard incorporating existing garage doors and proposed pedestrian gate | 2011-09-26 | Garage rear of 6 Bertie Terrace, Gulistan Road, Leamington Spa | Open space contribution | 100% on Commencement |  | Open Space Commuted Sum |  |  | February 2016:Contribution received but not yet spent | 916 |  |  |  | WDC Leisure
Warwick West | W/11/0074 | Outline application: residential development | 2012-02-14 | Aylesford School, Shelley Avenue, Warwick | Education | 50% occupation |  | Education |  |  | WCC pursuing contribution |  |  |  |  | WCC Education
Warwick West | W/11/0074 | Outline application: residential development | 2012-02-14 | Aylesford School, Shelley Avenue, Warwick | Highways | Other |  | Highways |  |  | February 2016:Received and part spent | 111100 |  |  |  | WCC Highways
Warwick West | W/11/0074 | Outline application: residential development | 2012-02-14 | Aylesford School, Shelley Avenue, Warwick | Open Space Design Scheme | 50% occupation |  | Open Space Design Scheme |  |  | February 2016:Open space design scheme currently being laid out. |  |  |  |  | WDC Leisure
Warwick West | W/11/0074 | Outline application: residential development | 2012-02-14 | Aylesford School, Shelley Avenue, Warwick | Open Space Commuted Sum | 100% Prior to Commencement |  | Open Space Commuted Sum |  |  | February 2016:Discussion ongoing with Developer |  |  |  |  | WDC Leisure
Kenilworth Abbey | W/11/0116 | Extensions to create 8 apartments | 2011-09-27 | 34 - 40 Warwick Road, Kenilworth | Contribution towards a public open space | On occupation of 1st dwelling |  | Open Space |  |  | February 2016:WDC Leisure pursuing contribution: property has changed hands - relevant party being sought.. | 3664 |  |  |  | WDC Leisure
Lapworth | W/11/0467 | Demolition and erection of buildings including 4 residential units | 2012-04-10 | Mill Lane and Old Warwick Road, Lapworth | Provision of affordable housing | Contract with appropriate affordable homes provider to be finalised with 6 months of commencement |  | Affordable Housing |  |  | Commuted sum agreed in lieu of on site provision. |  |  |  |  | WDC Housing
Lapworth | W/11/0467 | Demolition and erection of buildings including 4 residential units | 2012-04-10 | Mill Lane and Old Warwick Road, Lapworth | Commuted open space contribution | 100% prior to commencement |  | Open Space |  |  | February 2016:WDC pursuing contribution. | 5652 |  |  |  | WDC Leisure
Leamington Clarendon | W/11/1624 | Creation of new retail units and erection of flats and houses. | 2012-11-13 | 131 - 137 Regent Street, Leamington | Police contribution | Prior to occupation. | Towards provision of additional police infrastructure. | Police |  |  | February 2016:Warwickshire Police checking current position | 2376 |  |  |  | Warwickshire Police
Leamington Clarendon | W/11/1624 | Creation of new retail units and erection of flats and houses. | 2012-11-13 | 131 - 137 Regent Street, Leamington | Open space contribution | Prior to occupation. |  | Open Space |  |  | February 2016:Contribution being sought; WDC. Raj checking | 8792 |  |  |  | WDC Leisure
Leamington Clarendon | W/11/1624 | Creation of new retail units and erection of flats and houses. | 2012-11-13 | 131 - 137 Regent Street, Leamington | Prevention of occupants securing car parking permits. | Prior to occupation. |  | Parking |  |  | February 2016:WCC: contribution being sought. |  |  |  |  | WDC DM
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Affordable Housing | 50% Occupation |  | Affordable Housing |  |  | February 2016:Scheme progressing. 33 affordable homes occupied. |  |  |  |  | WDC Housing
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Affordable Housing | 95% Occupation |  | Affordable Housing |  |  | February 2016:Scheme progressing. 33 affordable homes occupied. |  |  |  |  | WDC Housing
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Open Space Design Scheme | Before development commences |  | Open Space Design Scheme |  |  | February 2016:Scheme submitted by Developer |  |  |  |  | WDC Leisure
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Open Space Commuted Sum | Prior to occupation of the last dwelling |  | Open Space Commuted Sum |  |  | February 2016:Discussions ongoing with developer |  |  |  |  | WDC Leisure
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Open Space Land Transfer | Prior to occupation of the last dwelling |  | Open Space Land Transfer |  |  | Scheme progressing. Trigger not yet reached. |  |  |  |  | WDC Leisure
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Education | 100% prior to 50% occupation |  | Education |  |  | Trigger not yet reached, site currently at 30% occupancy, expected Autumn 2016 | 783435 |  |  |  | WCC Education
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | GP Surgery | 100% prior to 50% occupation |  | GP Surgery |  |  | Trigger not yet reached, site currently at 30% occupancy, expected Autumn 2016 | 128130.51 |  |  |  | WDC Policy
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Library Contribution | 100% prior to 50% occupation |  | Library Contribution |  |  | Trigger not yet reached, site currently at 30% occupancy, expected Autumn 2016 | 35675 |  |  |  | WCC Libraries
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Police | 100% prior to 50% occupation |  | Police |  |  | Trigger not yet reached, site currently at 30% occupancy, expected Autumn 2016 | 82764 |  |  |  | Warwickshire Police
Whitnash | W/12/0027 | Residential development comprising 209 dwellings with associated garages, parking facilities, infrastructure, public open space, allotments, landscaping and access | 2012-09-26 | Land South of, St Fremund Way, Whitnash, Leamington Spa | Indoor Sports Facilities | 100% prior to 50% occupation |  | Indoor Sports Facilities |  |  | Trigger not yet reached, site currently at 30% occupancy, expected Autumn 2016 | 195731 |  |  |  | WDC Leisure
Leamington Milverton | W/12/1004 | Conversion of former library into 28 residential apartments, including extensions/alterations to building and associated parking and landscaping. | 2012-11-16 | York Road Centre, Formerly The Old Library, Avenue Road, Leamington Spa, CV31 3PR | Highways contribution | 100% on commencement |  | Highways |  |  | February 2016:WCC pursuing contribution. | 6400 |  |  |  | WCC Highways
Kenilworth Abbey | W/12/1371 | Development to provide 22 residential retirement units | 2013-02-04 | 48-50 Waverley Road, Kenilworth | Provision of affordable housing contribution | Prior to occupation |  | Affordable Housing |  |  | Paid in full: to be spent in Kenilworth | 248860 |  |  |  | WDC Housing
Warwick South | W/13/0464 | Erection on Continuing Care Retirement Community | 2013-07-08 | Land at Earl Rivers Avenue | Provision of affordable housing | Prior to occupation of 95% of the care units |  | Affordable Housing |  |  | First phase of scheme progressing including affordable housing. Trigger not yet met. |  |  |  |  | WDC Housing
Warwick South | W/13/0464 | Erection on Continuing Care Retirement Community | 2013-07-08 | Land at Earl Rivers Avenue | Provision of village transport service | On occupation. |  | Public Transport |  |  | WCC pursuing the scheme |  |  |  |  | WCC Highways
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Notification of Commencement of development | Prior to commencement |  | Commencement of development | No commuted sum | N/A | Development commenced | 0 |  |  |  | WDC DM
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Payment of Monitoring Fee | 100% Prior to Commencement |  | Monitoring | Paid in full on 7/7/15 | 30000 | Paid in Full: 7/7/15 | 30000 | N/A |  |  | WDC DM
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Affordable Housing Scheme Submission | Prior to commencement of development |  | Affordable Housing | No commuted sum |  | WDC pursuing the scheme | 0 |  |  |  | WDC Housing
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Amenity Open Space Land Scheme | Prior to the commencement of development |  | Open Space | No commuted sum |  | Land not ready, WDC pursuing | 0 |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Transfer Amenity Open Space Land | Prior to 50% occupation |  | Open Space | No commuted sum | N/A | February 2016: Development commenced. Open space not ready to transfer | 0 |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Layout & Install Amenity Open Space Land | Prior to 50% occupation |  | Open Space | No commuted sum | N/A | February 2016: Development commenced. Not yet laid out. | 0 |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Amenity Open Space Maintenance Sum | Prior to 50% occupation | As per the formula in the agreement | Open Space | No commuted sum | N/A | February 2016: Development commenced. To be calculated in due course. |  |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Play Area Equipment Contribution | 100% on Commencement |  | Play Area | Paid in full on 7/7/15 | 70000 | February 2016: Development commenced. Received contribution but not yet spent. This will fund a new play area on site | 70000 | N/A |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Layout of Play Area | On 50% occupation |  | Play Area | No commuted sum | N/A | February 2016: Development commenced. Play area to be developed when land is available. | 0 |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Play Area Commuted Sum | Upon completion of play area |  | Play Area | No commuted sum | N/A | February 2016: Development commenced. To be calculated in due course. |  |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Employment Opportunities | Prior to commencement |  | Employment Opportunities | No commuted sum |  | WDC pursuing details | 0 |  |  |  | WDC Economic Development
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Indoor Sports Facilities | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Indoor Sports Facilities | Paid in full on 7/7/15 | 172614.2 | Paid in Full: 7/7/15 | 172614.2 |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Heath Contribution South Warwickshire FT | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Health (Hospital) | Paid in full on 7/7/15 | 349049 | Paid in Full: 7/7/15 | 144188 | N/A |  |  | WDC DM
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Heath Contribution South Warwickshire FT | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Health (GP Surgery) | Paid in full on 7/7/15 | 144188 | Paid in Full: 7/7/15 | 346049 | N/A |  |  | WDC DM
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Outdoor Sports Facilities | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Outdoor Sport | Paid in full on 7/7/15 | 12480.6 | Paid in Full: 7/7/15 | 12480.6 | N/A |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Offsite Parks, Gardens & Allotments | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Open Space | Paid in full on 7/7/15 | 286880 | Paid in Full: 7/7/15. Proportion to be spent in Victoria Park | 286880 |  |  |  | WDC Leisure
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Education Contribution | 10% on occupation of the 1st dwelling; 50% upon occupation of 50% of the dwellings and the balance on the occupation of 90%. |  | Education | To be paid directly to WCC | N/A | February 2106: WCC invoicing for relevant amounts. | 1761100 |  |  |  | WCC Education
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Highways Contribution | 50% prior to occupation followed by 50% on 90% occupation |  | Highways | To be paid directly to WCC | N/A | February 2106: WCC invoicing for relevant amounts. | 792000 |  |  |  | WCC Highways
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Footpaths | 50% prior to occupation followed by 50% on 90% occupation |  | Footpaths | To be paid directly to WCC | N/A | February 2106: WCC invoicing for relevant amounts. | 3290.89 |  |  |  | WCC Highways
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | School Transport | 3 equal instalments, the first prior to occupation with the 2nd and 3rd instalments on the 2nd and 3rd anniversaries of that payment. |  | School Transport | To be paid directly to WCC | N/A | February 2106: Received in part. | 105000 |  |  |  | WCC Highways
Warwick South | W/13/0607 | Residential development up to a maximum of 220 dwellings and infrastructure | 2013-08-02 | Land North of Harbury Lane Heathcote, Warwick CV34 6TB | Sustainability Pack Contribution | Before development commences |  | Sustainability Pack Contribution | To be paid directly to WCC | N/A | Received | 11000 |  |  |  | WCC Highways
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Affordable Housing | 50% prior to 50% occupation |  | Affordable Housing | No commuted sum |  | Trigger not yet reached, site currently at 28% occupancy |  |  |  |  | WDC Housing
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Education Special Needs | Before development commences |  | Education | To be paid directly to WCC | N/A | February 2106: WCC invoicing for relevant amounts. | 18436 |  |  |  | WCC Education
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Footpaths | 50% prior to 50% occupation |  | Footpaths | To be paid directly to WCC | N/A | February 2106: WCC invoicing for relevant amounts. | 3560 |  |  |  | WCC Highways
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Health | 50% prior to 50% occupation |  | Health |  |  | Paid in Full 17/02/2016 | 72648.84 |  |  |  | NHS
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Highways | 50% prior to 50% occupation |  | Highways | To be paid directly to WCC | N/A | WCC invoicing for relevant amounts. | 342000 |  |  |  | WCC Highways
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Health | 50% prior to 50% occupation |  | Health |  |  | Paid in Full 17/02/2016 | 147857.3 |  |  |  | NHS
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Indoor Sports Facilities | 50% prior to 50% occupation |  | Indoor Sports Facilities | Request to be made in 3 months |  | Trigger not yet reached, site currently at 28% occupancy | 73753.34 |  |  |  | WDC Leisure
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Payment of Monitoring Fee | Before development commences |  | Monitoring Fee | In process, request made 20/8/15 |  | Payment overdue. WDC pursuing | 9198.39 |  |  |  | WDC DM
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Open Space | 50% prior to 50% occupation |  | Open Space | Request to be made in 3 months |  | Trigger not yet reached, site currently at 28% occupancy | 153163.82 |  |  |  | WDC Leisure
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Open Space | 50% prior to 50% occupation |  | Open Space | Request to be made in 3 months |  | Trigger not yet reached, site currently at 28% occupancy | 5332.62 |  |  |  | WDC Leisure
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Sustainability Pack Contribution | 100% on occupation of the 1st dwelling |  | Sustainability Pack Contribution | To be paid directly to WCC | N/A | February 2106:WCC invoicing for relevant amounts. | 4700 |  |  |  | WCC Highways
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Biodiversity off setting | No trigger |  | Biodiversity off setting | To be paid directly to WCC if applicable | N/A | February 2106:WCC invoicing for relevant amounts. | 88117 |  |  |  | WCC Ecology
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Sustainable Urban Drainage System | Before development commences |  | Sustainable Urban Drainage System | No commuted sum |  | WDC pursuing |  |  |  |  | WDC Drainage
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Employment Opportunities | Prior to commencement |  | Employment Opportunities | No commuted sum |  | WDC pursuing |  |  |  |  | WDC Economic Development
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | School Transport contribution | 50% prior to 50% occupation |  | School Transport contribution | To be paid directly to WCC | N/A | WCC pursuing | 28388
Whitnash | W/13/0858 | Outline application for residential development with all matters reserved apart from access | 2013-09-24 | Land to the South of Fieldgate Lane, Whitnash, Leamington Spa | Play Area | Prior to commencement |  | Play Area | In process, request made 20/8/15 |  | Paid in Full 17/02/2016 | 70000 |  |  |  | WDC Leisure
Manor | W/13/0897 | 51 sheltered elderly apartments | 2013-09-30 | Parmiter House, Arlington Avenue, Leamington Spa | Affordable Housing Contribution | Prior to occupation |  | Affordable Housing |  |  | Received | 225554 |  |  |  | WDC Housing
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Affordable Housing Scheme Submission | Prior to commencement |  | Affordable Housing | No commuted sum | N/A | Affordable Housing scheme received and agreed for 112 units. 13 completions to end Dec 2015 | 0 |  |  |  | WDC Housing
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Education | 10% on occupation of the 1st dwelling; 50% upon occupation of 50% of the dwellings and the balance on the occupation of 90%. |  | Education | To be paid directly to WCC | N/A | February 2016: WCC invoicing for relevant amounts. | 2241400 |  |  |  | WCC Education
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Footpaths | Prior to commencement |  | Footpaths | To be paid directly to WCC |  | February 2016: WCC invoicing for relevant amounts. | 10000 |  |  |  | WCC Highways
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Library Contribution | Prior to commencement |  | Library Contribution | To be paid directly to WCC |  | February 2016: WCC invoicing for relevant amounts. | 47754 |  |  |  | WCC Libraries
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Sustainability Pack Contribution | Prior to commencement |  | Sustainability Travel Pack Contribution |  |  | February 2016: WCC invoicing for relevant amounts. | 14000 |  |  |  | WCC Highways
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Hospital | 50% prior to 50% occupation and the remainder prior to 90% occupation |  | Hospital | Request likely in 6 months | 0 | February 2016: WCC invoicing for relevant amounts. | £1678 per dwelling |  |  |  | WCC Highways
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Amenity Space scheme provision | Prior to commencement |  | Open Space | No commuted sum |  | WDC pursuing: Land has been transferred and new owner contacted. To provide details of scheme. |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Transfer of Amenity Space | Following the provision of the amenity open space |  | Open Space | No commuted sum | N/A | Trigger not yet reached.Development commenced |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Submission of play area scheme. | Prior to commencement |  | Open Space | No commuted sum |  | WDC pursuing: Land has been transferred and new owner contacted. To provide details of scheme. |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Provision of play area | Prior to 50% occupation |  | Open Space | No commuted sum |  | Trigger not yet reached, site currently at 14% occupancy |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Provision of amenity space | Prior to 50% occupation |  | Open Space | No commuted sum |  | Trigger not yet reached, site currently at 14% occupancy |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Sustainable Urban Drainage System | Prior to Occupation |  | Sustainable Urban Drainage System | No commuted sum |  | Development commenced | 0 |  |  |  | WDC Drainage
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | GP Surgery | Prior to commencement |  | GP Surgery | In process, request made 20/8/15 |  | Payment now overdue, monitoring officer applying interest charge to late payment | 183512 |  |  |  | WDC DM
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Highways Contribution | 50% prior to 50% occupation and the remainder prior to 90% occupation |  | Highways | To be paid directly to WCC if applicable | N/A | February 2016: WCC invoicing for relevant amounts. | 1008000 |  |  |  | WCC Highways
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | School Transport contribution | For each phase to be paid in 3 equal instalments; the 1st to be paid prior to the occupation of dwellings in that area with the 2nd and 3rd paid on the 1st and 2nd anniversaries of that payment. |  | Highways | To be paid directly to WCC | N/A | February 2016: WCC invoicing for relevant amounts. | 84560 |  |  |  | WCC Highways
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Monitoring Contribution | Prior to the commencement of development |  | Monitoring |  |  | Paid in full 14/01/2016 | 30000 |  |  |  | WDC DM
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Biodiversity offsetting scheme | Prior to the commencement of development |  | Biodiversity | To be paid directly to WCC if applicable | N/A | February 2016: WCC invoicing for relevant amounts. |  |  |  |  | WCC Ecology
Bishops Tachbrook | W/13/1207 | Outline planning application for an urban extension comprising up to 280 new homes, public open space, landscaping, new access and highways and associated and ancillary development. | 2013-11-21 | Woodside Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QA | Employment and training strategy submission | Prior to the commencement of development |  | Employment | No commuted sum |  | WDC pursuing |  |  |  |  | WDC Economic Development
Warwick West | W/13/1490 | Demolition and conversion to provide 18 dwellings | 2013-12-09 | 2-22 Northgate Street, Warwick | Affordable Housing Contribution | Prior to occupation |  | Affordable Housing |  |  | Development commenced. Trigger not yet reached | 99100 |  |  |  | WDC Housing
Warwick West | W/13/1490 | Demolition and conversion to provide 18 dwellings | 2013-12-09 | 2-22 Northgate Street, Warwick | Sustainable Welcome Pack Contribution | Prior to occupation |  | Highways |  |  | Development commenced: trigger not yet reached. | 900 |  |  |  | WCC Highways
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Education | 50% prior to 50% occupation |  | Education |  |  | February 2016: trigger not yet reached. | 1601400 |  |  |  | WCC Education
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Education Primary | 50% prior to 50% occupation |  | Education |  |  | February 2016: trigger not yet reached. |  |  |  |  | WCC Education
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Country Park contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Country Park |  |  | February 2016: trigger not yet reached. | 153000 |  |  |  | WDC Policy
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Footpath contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Footpaths |  |  | February 2016: trigger not yet reached. | 3740 |  |  |  | WCC Highways
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | GP Surgery | 100% Prior to Commencement |  | GP Surgery |  |  | Paid in full 01/12/2015 | 154572 |  | 154572 |  | WDC DM
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Highways Contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Highways |  |  | February 2016: trigger not yet reached. | 1200000 |  |  |  | WCC Highways
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Hospital Contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Hospital |  |  | February 2016: development commenced: trigger not yet reached. | 335600 |  |  |  | WDC DM
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Indoor Sports Facilities | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Indoor Sports Facilities |  |  | February 2016: development commenced: trigger not yet reached. | 156922 |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Library Contribution | 100% prior to commencement |  | Libraries |  |  | February 2016: development commenced: trigger not yet reached. | 34138 |  |  |  | WCC Libraries
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Payment of Monitoring Fee | 100% Prior to Commencement |  | Monitoring |  |  | Paid in full 01/12/2015 | 30000 |  | 30000 |  | WDC DM
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Outdoor Sports Facilities | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Outdoor Sports Facilities |  |  | February 2016: development commenced: trigger not yet reached. | 11346 |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | School Transport | Prior to occupation of dwellings |  | School Transport |  |  | February 2016: development commenced: trigger not yet reached. | 60400 |  |  |  | WCC Highways
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Sustainable Urban Drainage System | Prior to commencement |  | Sustainable Urban Drainage System |  |  | February 2016: development commenced. Details being sought by WDC |  |  |  |  | WDC Drainage
Bishops Tachbrook | W/14/0023 | Residential development (approximately 200 dwellings) with new access onto Harbury Lane, land safeguarded for a new primary school, allotments, open space, local shop (A1 use up to 100 sqm gross), car parking and associated infrastructure | 2014-05-29 | Harbury Gardens, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QF | Open Space Land Transfer | Following provision of open space |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Affordable Housing | Before development commences |  | Affordable Housing |  |  | February 2016: development commenced. Details being sought by WDC | 0 |  |  |  | WDC Housing
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Open Space Commuted Sum | On provision of open space |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. | 0 |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Education | 50% prior to 50% occupation |  | Education |  |  | February 2016: development commenced: trigger not yet reached. | 402653 |  |  |  | WCC Education
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Footpaths | Prior to occupation of dwellings |  | Footpaths |  |  | February 2016: development commenced: trigger not yet reached. | 2140 |  |  |  | WCC Highways
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | GP Surgery | 100% prior to commencement |  | GP Surgery |  |  | February 2016: payment being requested -WDC. | 8723.34 |  |  |  | WDC Policy
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Highways | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Highways |  |  | February 2016: development commenced: trigger not yet reached. | 15000 |  |  |  | WCC Highways
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Hospital | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Hospital |  |  | February 2016: development commenced: trigger not yet reached. | 100680 |  |  |  | WDC Policy
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Indoor Sports Facilities | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Indoor Sports Facilities |  |  | February 2016: development commenced: trigger not yet reached. | 47076.8 |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Payment of Monitoring Fee | Prior to commencement |  | Monitoring |  |  | February 2016: payment being requested -WDC. | 30000 |  |  |  | WDC DM
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Highways | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Highways |  |  | February 2016: development commenced: trigger not yet reached. | 360000 |  |  |  | WCC Highways
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Offsite Parks, Gardens & Allotments | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. | 88457.29 |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Sustainable Urban Drainage System | 75% Occupation |  | Sustainable Urban Drainage System |  |  | February 2016: development commenced: trigger not yet reached. | 0 |  |  |  | WDC Drainage
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Outdoor Sports Facilities | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Outdoor Sports Facilities |  |  | February 2016: development commenced: trigger not yet reached. | 3403.8 |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Layout of Play Area | Before development commences |  | Play Area |  |  | February 2016: development commenced. Details being sought by WDC | 0 |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Play Area Commuted Sum | Upon provision of play area |  | Play Area |  |  | February 2016: development commenced: trigger not yet reached. | 0 |  |  |  | WDC Leisure
Radford Semele | W/14/0322 | Construction of up to 60 market and affordable dwellings, new vehicular access, open space and associated infrastructure (outline application including details of access) | 2014-06-06 | Land East of Radford Semele,North of Southam Road, Radford Semele, Leamington Spa, CV31 1TP | Sustainability Pack Contribution | Before development commences |  | Sustainability |  |  | February 2016: development commenced. Details being sought by WCC | 4500 |  |  |  | WDC DM
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Submission of Affordable Housing scheme | Prior to commencement of development |  | Affordable Housing |  |  | Approved scheme in place |  |  |  |  | WDC Housing
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Open Space and Play Area Design Scheme | Prior to commencement of development |  | Open Space |  |  | Expected within 2 months |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Open Space Land Transfer | Prior to 50% occupation |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Open Space Provision | Prior to 50% occupation |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Open Space Commuted Sum | Prior to the transfer of the open space | In accordance with the formula set out in the agreement | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Submission of biodiversity off setting scheme | Prior to the commencement of each phase of development |  | Biodiversity |  |  | February 2016: Development commenced. Information being sought by WCC |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Sustainable Urban Drainage System scheme | Prior to commencement of development |  | Drainage |  |  | February 2016: Development commenced. Information being sought by WCC |  |  |  |  | WCC Ecology
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Sustainable Urban Drainage System Commuted Sum | On the transfer of the SUDs Land |  | Drainage |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Drainage
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Submission of employment and training strategy | Prior to commencement of development |  | Employment |  |  | February 2016: Development commenced. Information being sought by WDC |  |  |  |  | WDC Economic Development
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Indoor Sports Facilities Contribution | 50% prior to the completion of 50% of the dwellings and the remainder prior to the completion of 90% of the dwellings for the relevant phase of development. |  | Sports |  |  | February 2016: development commenced: trigger not yet reached. | £831.04 per dwelling |  |  |  | WDC Policy
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Outdoor Sports Facilities Contribution | 50% prior to the completion of 50% of the dwellings and the remainder prior to the completion of 90% of the dwellings for the relevant phase of development. |  | Sports |  |  | February 2016: development commenced: trigger not yet reached. | £56.73 per dwelling |  |  |  | WDC Policy
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Provision of Play Area | Prior to 50% occupation |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Play Area Commuted Sum | On completion and transfer of the play area | In accordance with the formula set out in the agreement | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Police Contribution | 50% prior to the completion of 50% of the dwellings and the remainder prior to the completion of 90% of the dwellings for the relevant phase of development. |  | Police |  |  | February 2016: development commenced: trigger not yet reached. | £242.22 per dwelling |  |  |  | WDC DM
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Provision of a safeguarded land for education |  | To be safeguarded for a period of 5 years | Education |  |  | February 2016: Development commenced |  |  |  |  | WCC Education
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Education Contribution | For each phase of development, 10% on occupation of the 1st dwelling; 50% upon occupation of 50% of the dwellings and the balance on the occupation of 90%. |  | Education |  |  | February 2016: development commenced: trigger not yet reached. | £8007 per dwelling |  |  |  | WCC Education
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Highways Contribution | For each phase of the development, 4 equal instalments to be paid on the 1st occupation of market housing in that phase and then at 25%, 50% and 75%. |  | Highways |  |  | February 2016: development commenced: trigger not yet reached. | £6000 per open market dwelling |  |  |  | WCC Highways
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Public Transport Contribution | For each phase, to be paid in 5 equal instalments: the 1st prior to the occupation of the 100th dwelling in that phase with the remaining instalments to be paid on the 1st, 2nd, 3rd and 4th anniversary of that payment. | Towards the cost of extending and improving the no. 68 bus service and/or towards the provision of a new 20 minute service from the application site to Leamington railway station and the town centre. | Public Transport |  |  | February 2016: development commenced: trigger not yet reached. | £638 per dwelling |  |  |  | WCC Highways
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | School Transport contribution | For each phase to be paid in 3 equal instalments; the 1st to be paid prior to the occupation of dwellings in that area with the 2nd and 3rd paid on the 1st and 2nd anniversaries of that payment. | To provide bus services to serve the site and local secondary schools to provide transport to and from school. | Public Transport |  |  | February 2016: development commenced: trigger not yet reached. | £302 per dwelling |  |  |  | WCC Highways
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Sustainability Pack Contribution | For each area, prior to the commencement of development in that area. |  | Highways |  |  | February 2016: Development commenced. Information being sought by WCC | £75 per dwelling |  |  |  | WCC Highways
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Library Contribution | Prior to the commencement of the development |  | Libraries |  |  | February 2016: Development commenced. Information being sought by WCC | £21.89 per dwelling |  |  |  | WCC Libraries
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Hospital Contribution | 50% prior to the completion of 50% of the dwellings and the remainder prior to the completion of 90% of the dwellings in relation to each phase of the development. | Towards a new ward block at Warwick Hospital and additional treatment and patient facilities including community healthcare hubs at Warwick and Leamington | Health |  |  | February 2016: development commenced: trigger not yet reached. | £1,678 per dwelling |  |  |  | WDC DM
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | GP Surgery contribution | Prior to the commencement of the relevant phase of development | Towards the cost of a new GP surgery in Warwick District | Health |  |  | In process: WDC requesting payment | £764 per dwelling |  |  |  | WDC DM
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Payment of Monitoring Fee | Prior to the commencement of development |  | Monitoring |  |  | In process: WDC requesting payment | The lesser of £30,000 or 1% of total contributions |  |  |  | WDC DM
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Country Park contribution | Prior to the occupation of 50% of the dwellings for the relevant phase of development. |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. | £768 per dwelling |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Country Park scheme submission | Prior to the commencement of development |  | Open Space |  |  | Being progressed by WDC. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Provision of Country Park land. | Upon the completion of the 400th dwelling. |  | Open Space |  |  | February 2016: development commenced: trigger not yet reached. |  |  |  |  | WDC Leisure
Warwick South | W/14/0661 | Residential development of up to 785 dwellings, community hub, primary school, infrastructure and landscaping | 2014-09-19 | Land at Lower Heathcote Farm, Harbury Lane, Warwick | Rights of Way contribution | Upon occupation of the 1st dwelling within the development | Towards public right of way improvements within a 1.5 mile radius of the site. | Rights of Way |  |  | February 2016: development commenced: trigger not yet reached. | 12730 |  |  |  | WCC Footpaths
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Affordable Housing Scheme Submission | Prior to occupation |  | Affordable Housing |  |  | February 2016: Development commenced - Details being sought by WDC |  |  |  |  | WDC Housing
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Provision of Affordable Housing | 50% transferred to housing provider by 5% occupation of the market housing and the remainder by 95% Occupation |  | Affordable Housing |  |  | February 2016: Development commenced. Trigger not net reached. |  |  |  |  | WDC Housing
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Open Space Design Scheme | Before development commences |  | Open Space |  |  | February 2016: Development commenced - Details being sought by WDC |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Open Space Land Transfer | 50% Occupation |  | Open Space |  |  | February 2016: Development commenced. Trigger not net reached. |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Open Space Commuted Sum | Upon provision of the open space |  | Open Space |  |  | February 2016: Development commenced. Trigger not net reached. |  |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Biodiversity off setting | Before development commences |  | Biodiversity |  |  | February 2016: Development commenced - Payment being sought by WCC |  |  |  |  | WCC Ecology
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Sustainable Urban Drainage System | Before development commences |  | Drainage |  |  | February 2016: Development commenced - Details being sought by WDC |  |  |  |  | WDC Drainage
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Employment Opportunities | Before development commences |  | Employment |  |  | February 2016: Development commenced - Details being sought by WDC |  |  |  |  | WDC Economic Development
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Indoor Sports Facilities | 50% prior to 50% occupation and remainder prior to 90% occupation. |  | Sports |  |  | February 2016: Development commenced. Trigger not net reached. | £784.61 per dwelling |  |  |  | WDC Policy
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Outdoor Sports Facilities | 50% prior to 50% occupation and remainder prior to 90% occupation. |  | Sports |  |  | February 2016: Development commenced. Trigger not net reached. | £56.73 per dwelling |  |  |  | WDC Policy
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Play Area Commuted Sum | 100% on Commencement |  | Open Space |  |  | February 2016: Development commenced - Payment being sought by WDC | In accordance with the formulae set out in the agreement. |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Off site Play Area Contribution | Upon commencement |  | Open Space |  |  | February 2016: Development commenced - Payment being sought by WDC | £440 per dwelling |  |  |  | WDC Leisure
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Police Contribution | 50% prior to 50% occupation and remainder prior to 90% occupation. |  | Police |  |  | February 2016: Development commenced. Trigger not net reached. | 37533 |  |  |  | WDC DM
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Education Contribution | 10% prior to occupation of the first dwelling, 50% prior to 50% occupation, remainder prior to 90% occupation |  | Education |  |  | February 2016: Development commenced. Trigger not net reached. | £6639 per dwelling |  |  |  | WCC Education
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Highways Contribution | 50% prior to 50% occupation and remainder prior to 90% occupation. |  | Highways |  |  | February 2016: Development commenced. Trigger not net reached. | £6000 per dwelling |  |  |  | WCC Highways
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Sustainability Pack Contribution | 50% prior to 50% occupation and remainder prior to 90% occupation. |  | Highways |  |  | February 2016: Development commenced. Trigger not net reached. | £75 per dwelling |  |  |  | WCC Highways
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Library Contribution | 100% on Commencement |  | Libraries |  |  | February 2016: Development commenced - Payment being sought by WCC | £17.29 per dwelling |  |  |  | WCC Libraries
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Hospital Contribution | 50% prior to 50% occupation and the remainder prior to 90% occupation |  | Health |  |  | February 2016: Development commenced. Trigger not net reached. | £1678 per dwelling |  |  |  | WDC DM
Bishops Tachbrook | W/14/0689 | Development of 150 dwellings, school drop off, open space, landscaping, sustainable drainage systems, access, footpaths and associated infrastructure | 2014-08-22 | Land north of, Oakley Wood Road, Bishop's Tachbrook, CV33 | Payment of Monitoring Fee | 100% on Commencement |  | Monitoring |  |  | February 2016: Development commenced - Payment being sought by WDC | 30000 |  |  |  | WDC DM
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Provision of Affordable housing | 50% prior to 90% occupation of the market properties and 100% prior to 100% occupation. | 40% of the total no. of dwellings | Affordable Housing | No commuted sum | N/A | Trigger not yet reached, site currently at 22% occupancy |  |  |  |  | WD Housing
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Provision of open space | Prior to 75% occupation |  | Open Space | No commuted sum | N/A | Trigger not yet reached, site currently at 22% occupancy |  |  |  |  | WDC Leisure
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Biodiversity offsetting scheme | On Commencement |  | Ecology | No commuted sum |  | WCC pursuing |  |  |  |  | WCC Ecology
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Sustainable urban drainage scheme | Prior to commencement |  | Drainage | No commuted sum |  | Discussions ongoing |  |  |  |  | WDC Drainage
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Hospital contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% | To be used as set out in the agreement | Health |  |  | Trigger not yet reached, site currently at 22% occupancy | 100680 |  |  |  | NHS
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Indoor sports facilities contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% | Towards the cost of funding indoor sports halls and swimming pools in Warwick District | Sports |  |  | Trigger not yet reached, site currently at 22% occupancy | 47076 |  |  |  | WDC Policy
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Outdoor sports facilities contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% | Within Warwick District | Sports |  |  | Trigger not yet reached, site currently at 22% occupancy | 3403.8 |  |  |  | WDC Policy
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Off site parks and gardens contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% | Improvements to King George Playing Fields, Barford | Open Space |  |  | Trigger not yet reached, site currently at 22% occupancy | 86083 |  |  |  | WDC Leisure
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Police contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% | Towards provision of police infrastructure within the District | Police |  |  | Trigger not yet reached, site currently at 22% occupancy | 16818 |  |  |  | Warwickshire Police
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Education contribution | 10% on occupation of the 1st dwelling; 50% prior to 50% of the dwellings being completed and the remainder prior to 90% |  | Education | To be paid directly to WCC |  | Trigger for 10% reached and being sought BY WCC | 480420 |  |  |  | WCC Education
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Highways contribution | 50% prior to 50% of the dwellings being completed and the remainder prior to 90% | For the purpose of developing strategic highway infrastructure and carrying out measures to improve walking and cycling within the Leamington and Warwick area | Highways | To be paid directly to WCC |  | Trigger not yet reached, site currently at 22% occupancy | 216000 |  |  |  | WCC Highways
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Library contribution | By the occupation of 50% of the properties |  | Library | To be paid directly to WCC |  | Trigger not yet reached, site currently at 22% occupancy | 1038 |  |  |  | WCC Libraries
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Footpath contribution | On occupation of the 1st dwelling | For the improvement of public rights of way within 1.5 miles of the development | Footpaths | To be paid directly to WCC |  | Trigger reached: WCC pursuing | 3538 |  |  |  | WCC Highways
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Sustainability Travel Pack Contribution | On commencement |  | Sustainability Travel Pack Contribution | To be paid directly to WCC | N/A | Funds received | 4500 |  |  |  | WCC Highways
Budbroke | W/14/0693 | Full planning permission for 60 dwellings | 2014-09-16 | West of 22 Wellesbourne Road, Barford | Monitoring Contribution | Prior to the commencement of development |  | Monitoring | In process, request made 20/8/15 |  | Payment overdue and being sought by WDC. | 9595.74 |  |  |  | WDC DM