## Sheet1
Local Plan Suspension: Programme of Work
| 2015-09-01 | 2015-10-01 | Nov-15 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01
Memorandum of Understanding
Agree MoU at EPB
Endorse MoU at Council
Identify common ground with NBBC and review NBBC's SHLAA
Strategy Check and Review
Identify potential alternative options
Undertake high appraisal of alternative options
Identify revisions to the spatial strategy
Sustainability appriasal and HRA
Appoint consultants to undertake work
Appraise Growth options
Appraise Spatial options
Appraise Site Options
SA report
Agree HRA review scope with WCC ecology
Undertake HRA review
Report on HRA
Sites assessments
Stage 1: Identification of potential sites - Revisit existing SHLAA sites
Stage 1: Identification of potential sites -Undertake call sites
Stage 2: Technical and infrastructure assessment - existing SHLAA sites
Stage 2: Technical and infrastructure assessment -newly submitted sites
Stage 3: Policy compliance assessment
Stage 4 Shortlist of potential sites (assess viability, delivery, trajectory etc)
Final site selection
Implications for other aspects of the Plan
Establish Housing Trajectory
Establish 5 year land supply
Affordable housing policy
Employment Land provision
Prepare and agree modifications
Compile consultation version of modified Local Plan
Council approval for proposed modifications
Consultation
Consultation period
Organisation of Consultation responses
Consider possible further amendments
Submit Proposed modifications