## Sheet1
Local Plan Suspension: Programme of Work
| 2015-09-01 | 2015-10-01 | Nov-15 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01
Memorandum of Understanding
Agree MoU at EPB
Endorse MoU at Council
Identify common ground with NBBC and review NBBC's SHLAA | bar: 2015-12-01 to 2016-01-01
Strategy Check and Review
Identify potential alternative options
Undertake high appraisal of alternative options
Identify revisions to the spatial strategy
Sustainability appriasal and HRA
Appoint consultants to undertake work
Appraise Growth options
Appraise Spatial options
Appraise Site Options
SA report
Agree HRA review scope with WCC ecology
Undertake HRA review
Report on HRA
Sites assessments
Stage 1: Identification of potential sites - Revisit existing SHLAA sites
Stage 1: Identification of potential sites -Undertake call sites
Stage 2: Technical and infrastructure assessment - existing SHLAA sites | bar: 2015-12-01
Stage 2: Technical and infrastructure assessment -newly submitted sites | bar: 2015-12-01
Stage 3: Policy compliance assessment | bar: 2015-12-01
Stage 4 Shortlist of potential sites (assess viability, delivery, trajectory etc) | bar: 2015-12-01
Final site selection | bar: 2016-01-01
Implications for other aspects of the Plan
Establish Housing Trajectory | bar: 2016-01-01
Establish 5 year land supply | bar: 2016-02-01 to 2016-03-01
Affordable housing policy | bar: 2015-12-01
Employment Land provision | bar: 2015-12-01
Prepare and agree modifications
Compile consultation version of modified Local Plan | bar: 2015-12-01 to 2016-01-01
Council approval for proposed modifications | bar: 2016-01-01
Consultation
Consultation period | bar: 2016-02-01 to 2016-03-01
Organisation of Consultation responses | bar: 2016-03-01 to 2016-04-01
Consider possible further amendments | bar: 2016-04-01 to 2016-05-01
Submit Proposed modifications | bar: 2016-05-01