## Sheet1
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other |  | Other Potential
[9 empty] | Committed Funding |  | Funding
PHYSICAL INFRASTRUCTURE
Transport: Sustainable Travel Infrastructure (Non Corridor specific)
T1 | Smarter Choices | Implementation of a range of behavioural measures such as workplace travel plans, sustainable transport packages for new residents, travel awareness campaigns, public transport information, car clubs and car sharing and teleworking, home working and home shopping. | 1 | 1000000 |  | 1000000 |  | £1,000,000 |  |  |  | *Travel pack monies agreed in S106 from Southern sites is £350,000 thus far. | Early 2017 - 2022 and onwards throughout plan period
Funding also used for road safety/ education in schools
Transport Infrastructure: A452 Europa Way Corridor
T2 | Refer to appendix A that itemises the infrastructure components that are required for this corridor. | Major carriageway and junction improvements (including pedestrian and cycleway provision / connectivity). Includes Europa Way Corridor parts 1 and 2, Europa , Myton Road Roundabout, Shires Retail Park Roundabout, Grey's Mallory Roundabout. | 1 | 37000000 |  | 17500000 | 18700000 | 36200000 | £3,600,000 Growth Deal bid secured. |  | £3,000,000 potentially from strategic development proposals in Stratford District | *Note- all factors within this Corridor to be subject to a WCC SEP bid for finance. In general some £17.5million has been agreed via S106 Agreements to date for highways improvements- this can be utilised for carriageway / cycling measures as deemed necessary. A considerable amount of this corridor project will be delivered from S278 Agreements/ arrangements.It is anticipated that a detailed schedule and plan of how the various components that make up this corridor programme will be produced and made available by mid-2017. | Early 2017-2022
Transport Infrastructure: A452 Leamington to Kenilworth Corridor
T3 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Includes carriageway and junction improvements as well as the provision of a park and ride facility and cycle route enhancements K2L. Includes cost of dualling of A452. |  | 17900000 |  | 6000000 |  | 6000000 |  |  | Highways England , RIS2 and future potential from S278 | . | Medium priority 2022-2027
|  | Cycle and Bus Priority Measures for the A452 Corridor (Kenilworth to Leamington) |  | 1000000 | 1000000 |  |  | 1000000
|  | North Leamington Park and ride |  | 1500000 | 1500000 |  |  | 1500000 |  |  |  |  | TBC
Transport Infrastructure: Warwick-Leamington-Lillington (via Emscote Road)
T4 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Multi modal improvements Includes carriageway improvements and junction improvements to the following : Emscote Rd / Greville Road, Princess Drive/ Warwick New Road, A445/ Lillington Avenue/ Lillington Road. |  | 1660000 | 1660000 |  |  | 1660000 |  |  | Emscote road works, Princes drive junction may be recipients of SEP bid finance |  | Early to medium 2017-2027
Transport Infrastructure: Leamington South (including Tachbrook Road)
T5 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Multi modal improvements,Includes carriageway improvements and junction improvements to Princes Drive / Park Road, Bath Street Gyratory,Adelaide Road/ Avenue Road, Dormer Place/ Adelaide Road. |  | 3900000 | 3900000 |  |  | 3900000 |  |  | £120,000 from strategic development proposals in Stratford District | *Note- all items within this Locality to be subject to a WCC SEP bid for finance. | early-medium 2017-2027
|  | Sydenham Drive / Radford Road potential widening |  | 653000 |  |  | 653000 | 653000
Transport Infrastructure: Warwick Town Centre to Heathcote via Gallows Hill
T6 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Includes carriageway improvements and junction improvements |  | 5200000 |  |  | 5200000 | 5200000 |  |  | £180,000 from strategic development in Stratford District |  | Medium 2023-2028
Specific road improvements – (two lanes to both Banbury Road and Gallows Hill).
Transport Infrastructure: Warwick Town Centre to Leamington (via Myton Road)
T7 | Refer to appendix A that itemises the infrastructure components that are required for this corridor. | Myton Road Roundabout - synchronisation of signaling system |  | 1204000 |  |  | 1204000 | 1204000 |  |  | Potential for funding from SEP / Growth Deal Bid | Details in Europa Way and Warwick Town Centre to Heathcote via Gallows Hill corridors | Early 2017-2022
Transport Infrastructure: A429 Coventry Road, Warwick
T8 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Coventry Road / Spinney Hill Roundabout |  | 1140000 | 1140000 |  |  | 1140000 |  |  |  |  | Medium 2022-2027
Transport Infrastructure: A425 Birmingham Road, Warwick
T9 | A46/A425/A4177 Birmingham Road ‘Stanks Island’ |  | 1 | 6000000 |  | 300000 |  | 300000 | £3,500,000 from SEP |  |  |  | Early 2017-2022
£2,600,000 from WCC Corporate Growth Fund
Transport Infrastructure: A46 to Cubbington
T10 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Bericote Rd / Stoneleigh Rd, Kenilworth Road /Westhill Roiad, A445/Sandy Lane |  | 2338000 |  | 2338000 |  | 2338000 |  |  |  | Confirmation of assignation to CIL / S106 yet to be confimed by County Highways | ??
Transport Infrastructure: Strategic corridor improvements
T11 | M40 Motorway Traffic Management and A46 Expressway Upgrade to improve linkages with M5 and M6 | Provision of Smart Motorways between J14 and J15 of the M40 |  | n/a | [6 empty] | S106 contributions from strategic development in Stratford District | The Local Plan evidence base highlights that WDC Local Plan growth is not the trigger for major improvements to the strategic motorway network. | late 2027 and beyond
These capacity concerns will have to be addressed before the end of the Plan period. The precise identification and costing of any improvements is yet to be determined and there is potential for any scheme(s) to be predominantly financed / delivered by HE/ DfT
Transport Infrastructure: Kenilworth Locality Improvements
T12 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Including improvements to Kenilworth Gyratory,A45/ Kenilworth Road,A429 / Stoneleigh Road/ Gibbett Hill Road. |  | 503000 |  | 503000 |  | £503,000 |  |  |  | Note nominal contribution to A45/ Kenilworth Road and A429 Stoneleigh Road/ Gibbet Hill Road yet to be identified | Early - medium 2017-2028
|  | Stoneleigh Road / A46/ Dalehouse Ln/ Stoneleigh Rd |  | 20000000 |  |  |  |  | 20000000 | growth deal |  | Dft funding transferred from A45/ A429
Transport Infrastructure: Sub-regional Employment Site
T14 | Transport Infrastructure Associated with Sub-regional employment site | The recently approved planning application at Whitely South incorporates the delivery of the infrastructure set out below. | [9 empty] | It should be noted that the South of Whitely application does not cover the total that is allocated in the Local Plan for employment purposes and further requirements (and consequently additional contributions may be sought / forthcoming). | Early - 2017-2022
• New junction on A45 between Festival and Toll Bar islands including bridge over A45 to link site with Jaguar Whitley Business Park (Coventry)
|  | • New access road within the site to link the two zones (east of Baginton and south of Middlemarch Business Park). | [9 empty] | Details of the financial arrangements for this area are emerging and will be available before the Local Plan EIP. It is anticipated that many of the large scale infrastructure requirements will be funded from a Growth Bid submitted by JLR.
• New roads within the Jaguar Whitley Business Park (Coventry)
|  | • Improvements to capacity of Festival island (Coventry) and the A46/Stoneleigh Road junction | [9 empty] | A further package of funding directly attributable to the Whitley South planning application will also be available subject to the successful grant of the consent (currently being considered by the Secretary of State).
• Enhancement to Stivichall bypass/London Road bypass junction
|  | • New roundabout at junction of Bubbenhall and Stoneleigh Roads. | [9 empty] | )
• New bus route with high quality infrastructure and frequent services between Coventry City Centre and site.
• Extensive improvements to off-site footpaths and cycleway links.
• Measures to restrict traffic from the site entering/exiting along Rowley Road/Bubbenhall Road.
T15 | Transport Infrastructure: Town Centre Strategies
|  | Town Centre Strategies, Leamington Spa, Warwick, Kenilworth | 1 | 5000000 | 5000000 |  |  | 5000000 |  |  |  | £2 M Leamington Spa, £2M Warwick, £1M Kenilworth | Early 2017-2022
|  | Castle Hill Gyratory Signals |  | 876000 |  | 876000 |  | 876000
|  | Improvements to Priory Road Smith Street and St Nicholas Church Street |  | 626000 |  | 626000 |  | 626000
T16 | Cycling,bus priority measures and other sustainable transport schemes not specified in Appendix B of the 2016 STA |  |  | 2000000 | 2000000 |  |  | 2000000
| Transport Infrastructure Total |  |  | 109500000 | 16200000 | 29143000 | 25757000 | 71100000 | 29700000 |  | 3300000 | *Total transport finance from S106 thus far £17,500,000 – includes footpaths, highways / cycleways, travel packs and public buses.
| Telecommunications | [10 empty] | Refer to appendix 1
| Utilities: Electric and Gas | [10 empty] | Refer to appendix 1
| Utilities: Water and Sewage | [10 empty] | Refer to Appendix 1
Utilities: Waste
W1 | Household Waste and Recycling | Redesign of existing household recycling facilities to accommodate population increase. | 2 | 575000 | 460000 |  |  | 460000 | 115000 |  |  |  | Medium 2023 - 2028
| Waste: Sub Total |  |  | 575000 | 460000 | 0 |  | 460000 | 115000
SOCIAL INFRASTRUCTURE
| Education: Primary Schools | [7 empty] | £39,000,000 |  |  | *Note: Education contributions from S106 currently stand at £39,000,000 This is to be utilised for all types of school requirement.
E1a | New Primary Schools | Heathcote Primary School (1 x 2 form) | 1 | 3500000 |  | 3500000 |  | 3500000 | 3500000 |  |  | *Land secured through S106 Planning permission given and construction team now on site. | Early 2017- 2022
[9 empty] | Forward funded by WCC in advance of S106 receipts – school to be a free school academy run by the Community Academies Trust. |  |  | The school is due to open at one form of entry (i.e. 30 pupils per year group) in September 2017. The school will then expand as demand requires. The school will not admit in all year groups initially although this will be kept under review.
Safe school zone (a signalised/ toucan pedestrian crossing)on Harbury lane required in parallel with this project.
E1b | New Primary Schools | Grove Farm (Oakley Grove) Primary School (1 x 1 form) | 1 | £3.400,000 |  | £3.400,000 |  | £3.400,000 |  |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. | *Land secured / identified through S106 | Medium 2023-2028
To be funded through S106
Note – Gallows Hill contribution of £1,694,000 to this primary school
On-going discussions with the developer has enabled the provision of additional land should this be required. This will enable the proposed school to be built to 2 forms of entry.
E1c | New Primary Schools | Myton / West of Europa Way (1 x 2 form) | 1 | 6000000 |  | 6000000 |  | 6000 |  |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. Assumed existing S106 contributions will cover this | *Location to be adjacent Myton School details being developed through master planning arrangements | Medium 2023-2028
Exact location yet to be determined
E1d | New Primary Schools | Whitnash East / South Sydenham (1x 1 form) | 1 | [7 empty] | Will be funded as a free school if required | Possible location of a free school if required.
E1e | New Primary Schools | Thickthorn school (1x1 form) - located at Thickthorn. | 1 | 6000000 |  | 6000000 |  | 6000000 |  |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. | *WCC will negotiate land requirements and financial contributions as part of the planning process. In all cases there will be an aspiration for new provision to be built in such a way there is provision to expand longer term, hence allowing sustainability. | Early - 2017-2022
[11 empty] | Expansion of existing schools will need to be funded through Developer contributions | Current policy requires the new schools to be Free Schools.
The increased number of dwellings associated with further allocations in the Kenilworth area will also create the need for further new primary provision.
This could be through primary / secondary facility at
secondary facility at Southcrest Farm.
The expansion of an existing primary school in the Kenilworth area may also be given consideration.
E1f | New primary Schools | Kings Hill Allocation - (based on 2000 dwellings) 1x 2 form entries. | [9 empty] | Estimated pupil yield for 4000 dwellings suggests the need for 5 forms of entry at primary school age. | Early 2017-2022
|  | Note: Education planning requires consideration for requirements across the entire proposed site i.e. 4000 dwellings and discussions with developers have been on this basis) | [9 empty] | The pattern of provision is still to be determined although the possibility of a primary / secondary all through school is being discussed.
Discussions have taken place with Coventry City Council to ensure we don’t over provide places and put existing schools at risk.
Discussions have confirmed that there is no surplus capacity of school places in the neighbouring part of Coventry.
It is difficult to estimate costs until a solution for the provision of places is identified.
Eig | New Primary Schools (Asps) | Asps’ obligation reserves land for a primary school, one form entry plus pre-school; 1.1 acres and primary school funding package. |  | 2900000 |  | 2900000 |  | 2900000 |  |  | Any additional costs to be funded by the EFA. | Paid for by the Asps development S106 | Medium 2023-2028
E2a | Expansion of existing schools (Whitnash) | Whitnash Primary School – 0.5 form entry additional capacity | 1 | 1500000 |  | 1500000 |  | 1500000 |  |  |  |  | Early 2017 - 2022
E2b | Expansion of existing school (Barford) | Development of additional capacity at Barford Primary School | 1 | 500000 |  | 480000 |  | 480000 | 20000 |  |  | Expansion has been forward funded by WCC with S106 contributions being collected as appropriate. | Early 2017-2022
The expansion to 1 Form of Entry will still allow the possibility of children from outside the priority area being able to secure a place at the school (i.e. it allows for some ‘spare’ capacity)
| Expansion of existing school (Budbrooke) | Budbrooke to be expanded from 1.5 form entry to 2 form entry to cater for additional demand in respect of new allocations in the vicinity(Hampton Magna / Hatton Park) |  | 1500000 |  | 1500000 |  | 1500000 |  |  |  | Budbrooke Primary School is now managed by the Community Academies Trust. | Early 2017 - 2022
The Trust and the Local Authority work closely together and there is still an aspiration for the school to expand to 2 forms of entry.
E3 | Village schools | No additional requirement. The provision of additional capacity as set out in E1, E2 and E3, combined with displacing children out of priority area means that the proposals for new development in villages can be met at the following schools: | [9 empty] | The need to maintain the viability of village schools is vital. Development in excess of Local Plan numbers will mean that it is no longer possible for WCC to provide local school places.
• Bishops Tachbrook
|  | • Cubbington | [9 empty] | * Developers have been required to contribute towards the cost of school places elsewhere as well as a contribution towards home to school transport costs.
• Budbrooke
• Lapworth
• Radford Semele
• Burton Green
• All Saint’s Leek Wootton
| Primary Schools - Sub Total |  |  | 25300000 |  | 25280000 |  | 25280000 | 20000
Education: Secondary Schools
| South of Warwick Sites | [10 empty] | The delivery of additional secondary school places will be delivered through a phased approach.
(Overview)
The first phase will see the expansion of Campion School and discussions are taking place between the Academy and the Local Authority.
Phase 2 is likely to see the provision of a new free school on reserved land.
We are aware that The Trinity School has expressed an interest in changing their existing offer and this will be a consideration.
Discussions will continue with all existing providers.
E4 | South of Warwick: Southern Sites | See above | 1 | To be quantified | [7 empty] | *Additional Land secured through S106. Note Myton expansion project (if required) to be funded by Section 106
Note: Asps contribution is now relevant to this matter:-
£3,100,000 contribution towards the cost of expanding existing secondary schools ,
Further £650,000 towards post 16 educational requirements.
Note Gallows Hill to contribute £1,900,000 towards secondary school accommodation at or adjacent to Myton School.
(Both of the above are included in the ‘global’ total of £39,000,000) detailed at the head of this section of the IDP.
E5 | Whitnash East | Expansion of Campion School | 1 | 8150000 |  | 8150000 |  | 8150000 |  |  |  | The cost estimate is for the whole expansion costs and not just those associated with Whitnash East. | Early 2017-2022
E6 | Kenilworth | There is an aspiration for Kenilworth School to relocate both of the existing school sites on to one new site at Southcrest farm. | 1 | 38200000 |  | 7600000 |  | 7600000 |  |  | Note: - A significant contribution may come from existing school site land sales. | *Scheme being investigated – | Early 2017-2022
This is supported by both Warwick District Council and Warwickshire County Council.
Development of an all through (11-18) Kenilworth School in place of the current split site Kenilworth School should not solely be funded by Developer contributions as the scheme is not the result of increased pupil numbers.
Potential to co-locate primary school on this site
The proposed growth within Kenilworth Town requires the need for expansion of provision at Kenilworth School.
The proposed development at Kings Hill will require its own secondary provision.
E7 | Kings Hill Allocation | As site proceeds to 4000 dwelling capacity (beyond plan period /2000 threshold) land should be reserved to cover the possibility of a new ‘all-through’ primary / secondary school and Special Educational needs facilities. |  | To be quantified | [7 empty] | The provision of 4,000 homes will require a minimum of 5 form of entry for education purposes. | Medium 2023-2028
Proposed development at Westwood Heath will also require the provision of additional capacity and this could see the need for 6 or 7 forms of entry in total at secondary age.
Discussions are taking place with the developers but the need for on-site secondary provision is agreed.
Provision will need to be funded from developer contributions and possible forward funding from EFA as part of the provision of free schools.
E8 | North of Milverton / Blackdown / Stoneleigh Road allocations | Expansion of existing school provision, possibly North Leamington and / or The Trinity School |  | To be quantified
E9 | Other Sites | Unspecified expansion to primary and secondary schools | 2 | £2,500,000 | 2500000 |  |  | 2500000 |  |  |  |  | Medium 2023-2028
| Secondary Schools Sub Total |  |  | 48850000 | 2500000 | 15750000 |  | 18250000
Education : 0-5 Provision
E10 | District-wide facilities | Contribution to improvement and expansion of existing facilities – details to be confirmed | 2 | 1200000 | 1200000 |  |  | 1200000 | Asps contribution 408,600 |  |  | It is the aspiration of WCC that all new primary schools will have pre-school provision on site, either run by the school itself or by a private provider. | Early 2017 onwards
This cannot be guaranteed however as the Free Schools agenda rolls out and WCC have less control.
WCC will continue to seek pre-school contributions from developers to ensure a sufficient supply of pre-school provision.
Education: Special Educational Needs Provision
E11 | District-wide facilities | Contribution to improvement and expansion of existing facilities – details to be confirmed | 1 | 1340000 | 1340000 |  |  | 1340000 | Asps £168,300 towards SEN requirements |  |  | Wherever possible WCC will look to support a child attend their preferred school through adaptations to existing schools. | Early 2017 onwards
S106 contributions will be collected from developers to ensure that this can continue.
School Transport
E12 | Contribution to school transport |  |  | 1870000 |  | 1870000 |  | 1870000 |  |  |  | Requests in support of home to school transport costs will be made if excessive development takes place within villages and local school places cannot be provided e.g. Radford Semele | Medium 2023-2028
| Education Other : Sub Total |  |  | 4410000 | 2540000 | 1870000 |  | 4410000 | 576900
| EDUCATION TOTAL |  |  | 78560000 | 5040000 | 42900000 |  | 47940000 | 596900
| Health: Acute and Community Health Services |  | The Health Trust proposes to meet infrastructure requirements through development projects, including new wards, inpatient facilities, outpatient clinic suites, associated diagnostic and intervention facilities and support service infrastructure at the Trust’s hospital sites. Note £977,000 to go to acute healthcare from the Asps. Gallows Hill will deliver £476,550 for acute healthcare provision. Note above figures are incorporated in the overall WDC S106 total. *Total agreed S106 (thus far) for hospital provision -£5,800,000
H1 | Warwick Hospital | First ward block at the Warwick Hospital site – the main provider of acute hospital services. | 1 | 12000000 |  | 4000000 |  | £4,000,00 |  |  | £4,000,000 NHS | *Delivered but forward funded – money recouped from WDC/SDC developer contributions. | Early 2017-2022
£6,000,000 overall available from S106 agreements in Warwick District thus far
[9 empty] | £4,000,000 - SDC |  |  | £977,000 to go to acute healthcare from the Asps
Gallows Hill will deliver £476,550 for acute healthcare provision
Note above figures are incorporated in the overall WDC S106 total
H2 | Warwick Hospital | Additional outpatient, diagnostic, treatment and in-patient facilities, including hubs for community health care teams at Warwick and Stratford Hospitals - it is recognised that the first New Ward Block and Stratford Hospital projects will not fully meet the healthcare demand associated with the new population growth projections and we will require additional infrastructure to deliver future acute and community healthcare requirements on a sustainable basis | 2 | 12000000 | 4000000 |  |  | £4,000,00 | 4000000 |  | £4,000,000 NHS |  | Early 2017-2022
[9 empty] | SDC |  |  | Section 106 costs from WDC/SDC
H3 | Stratford Hospital | A new hospital at our Stratford Hospital site including outpatient, diagnostic, treatment and inpatient facilities and a hub for community healthcare teams. (Target completion for Phase 1 by Autumn 2015).This is integral to enabling additional capacity at Warwick Hospital |  | 40000000 | 8500000 |  |  | 8500000 | 8500000 |  | £23,000,000 NHS | Development underway –anticipated completion 2017 | Early 2017 - 2022
SDC
CIL apportionment to be shared with Stratford District Council
| Health – Hospital Sub Total |  |  | 64000000 | 12500000 | 4000000 |  | 16500000 | 16500000 |  | 31000000
| Health: GP Services |  | It should be noted that due to a change in responsibilities in the health sector the District Council is currently discussing a review of primary healthcare requirements with the CCG. Necessary requirements may involve a combination of initiatives involving collaborative working between groups of surgeries to provide more effective services to the public as well as new ways of delivering services including greater use of IT. This may be combined with necessary physical enhancements to existing GP surgeries (where necessary / possible). Confirmation of the CCG’s preferred / precise strategy is still required. | [8 empty] | *Total currently achieved through S106 £2,650,000
Note CCG currently being asked to ‘refresh’ list of requirements if necessary
H4 | Warwick: Southern Sites | A new 5 GP medical centre to be provided land at Myton/ West of Europa Way | 1 | 2900000 |  | 2900000 |  | 2900000 |  |  |  | *Site being identified through detailed through detailed planning negotiations. | Medium 2023-2028
Funds committed/ to be made available through S106 agreements.
H5 | Warwick Gates medical centre | Expansion / additional works to improve existing medical centre |  | 115000 |  | 115000 |  | 115000 |  |  |  | Note £113,000 of S106 finance will fund these additional works to the existing surgery at Warwick Gates | Early 2017-2022
H6 | Kenilworth | Expanded medical facilities to meet the needs of additional development. | 1 | 140000 |  | 126000 |  | 126000 | 14000 |  |  |  | TBC
H7 | Whitnash / Sydenham / Radford Semele | Expansion of existing medical centre - potentially Croft Medical Centre | 1 | 95000 |  | 73000 |  | 73000 | 22000 |  |  |  | TBC
H8 | Lillington / Cubbington | Extension to Cubbington Road Surgery | 1 | 40000 |  | 40000 |  | 40000 |  |  |  |  | TBC
H9 | Urban Sites | Combining of existing practices |  | 400000 | 400000 |  |  | 400000 |  |  |  |  | TBC
| Health - GP Sub Total |  |  | 3690000 | 400000 | 3254000 |  | 3654000 | 36000
| HEALTH TOTAL |  |  | 67690000 | 12900000 | 7254000 |  | 20154000 | 16536000 |  | 31000000
| Indoor Sports Facilities: Sports Halls and Swimming Pools | [10 empty] | *£3,100,000 identified in Southern sites S106’s
ISF1 | Improvements to sports hall and swimming pools | Refurbishment and expansion of swimming pools, sports halls and gym facilities in Kenilworth, Leamington and Warwick. This is required partly as a result of population growth: | [10 empty] | Early 2017-2022
|  | • a deficit of 6.5 badminton courts in total |  | £24,000,000 (Total) |  | 500000 |  |  | £2,000,000 Sport England |  |  | Works to redevelop Newbold Comyn and St Nicholas Park Leisure centres are underway.
• by 2022 swimming pools will be full. Therefore there is a need to modernise, increase the capacity of the swimming pools (plus 35sq m pool area) and improve the changing and circulation areas to improve the quality of the swimming pools.
|  | Indoor fitness stations need enhancing / additional 61-138 stations) |  | Phase1 (Newbold Comyn and St Nicholas centres)- £12,000,000 |  |  |  |  | £9,500,000 - WDC
|  |  |  | Phase 2 – (Abbey Fields / Castle Farm) | 5200000 |  |  | 5200000
12000000
| Indoor Sports: Sub Total |  |  | 24000000 | 5200000 | 500000 |  | 5700000 | 11500000
| Cultural Facilities: Library Services | [10 empty] | *£175,202 identified in Southern sites s106’s
CU1 | Contributions to Library Service | IT and stock purchases to support growth in population. | 2 | 155000 |  | 155000 |  | 155000 |  |  |  | The County Council does not currently have plans to deliver new library provision. | Medium 2023 -2028
Financial contributions are requested for all new developments of more than 24 dwellings to ensure that the service is able to provide appropriate stock as well as delivering targeted promotions.
Cultural Facilities: Arts and Culture
CU2 | Kenilworth Public Service Centre and Community Theatre | Provide new public service centre along with a community theatre in line with the proposals consulted on for the Kenilworth Town Plan |  | 5200000 | 4200000 |  |  | 4200000 |  |  | 1000000 |  | Medium 2023-2028
assumed from sale of current Talisman theatre site
0
| CULTURAL FACILITIES |  |  | 5355000 | 4200000 | 155000 |  | 4355000 |  |  | 1000000
TOTAL
| Emergency Services | [10 empty] | *£950,000 identified in Southern sites S106’s for police infrastructure
ES1 | Police: Custody Suite | 12 additional cells needed | 2 | 500000 | 500000 |  |  | 500000
ES | Police: Safer Neighbourhood Team Police Office | Additional offices at Europa Way | 1 | 450000 |  | 450000 |  | 450000 |  |  |  |  | Medium 2023-2028
2a
ES | Police: Safer Neighbourhood Team Police Office | Additional office at Lower Heathcote Farm |  | 450000 |  | 450000 |  | 450000 |  |  |  |  | Medium 2023-2028
2b
ES | Police: Safer Neighbourhood Team Police Office | Additional office at Thickthorn |  | 450000 |  | 450000 |  | 450000 |  |  |  |  | Medium 2023-2028
2c
ES2d | Police: Safer Neighbourhood Team Police Office at the Asps | Additional office at Asps plus £188,000 for fitting out etc to be delivered by developers (agreed in legal obligations) | [6 empty] | Additional office at Asps plus fitting out met in Asps obligation. |  |  |  | Medium 2023-2028
ES3 | Other police equipment and costs | A range of other “CIL Compliant” costs including vehicles, communications technology and surveillance equipment, training, uniform and personal equipment | 2 | 500000 | 500000 |  |  | 500000 |  |  |  |  | Medium 2023-2028
ES4 | Ambulance Service | The service has undertaken a recent premises review. They have no further premises requirements during the Plan Period | N/A | 0 | [7 empty] | The Ambulance Trust is keen to work with Developers to support the provision of defibrillators. | Medium - 2023-2028
WCC supports requests for the provision of defibrillators on all new public buildings either through direct provision of the payment of a financial contribution. (Approx cost per defib is £1,500)
|  |  |  | 2350000 | 1000000 | 1350000 |  | 2350000
Community Facilities
CF1 | Warwick: Southern Sites Community Centre | New Community Centre, including 1 year start-up costs | 1 | 1200000 | 1200000 |  |  | 1200000 | 250000 |  |  |  | Early 2018-2022
CF1 | South of Harbury Lane Community Centre | New Community Centre, including 1 year start-up costs | 2 | 1200000 | 1200000 |  |  | 1200000 |  |  |  |  | Medium 2023-2028
CF2 | Kenilworth: Thickthorn Community Centre | New Community Centre, including 1 year start-up costs | 1 | 1200000 |  | 1200000 |  | 1200000 |  |  |  |  | Medium 2023-2028
CF3 | Kings Hill Community Centre / hall | New Community Centre, including 1 year start-up costs | 2 | 1200000 |  | 1200000 |  | 1200000 |  |  |  |  | Medium 2023-2028
Village Infrastructure
V1 | Village Infrastructure | The proposed housing allocations for the growth villages will require (over and above any educational requirements) associated infrastructure investments. For example this could include facilities for teenagers; sport and recreation facilities; improved community halls; allotments; nursery provision; local road improvements etc. | [10 empty] | TBC
|  |  |  | 4800000 | 2400000 | 2400000 |  | 4800000 | 250000
GREEN INFRASTRUCTURE
Country parks and Strategic Green Infrastructure
GI1 | Tach Brook Country Park | 62.5 hectare Country Park to north side of Tach Brook providing a separation and recreational space between Bishops Tachbrook and proposed new development to the south of Harbury Lane. Include pedestrian and cycle access, links to wider countryside, and ecological areas. Costs include maintenance and management for 13 years. | 1 | 2300000 |  | 2300000 |  | 2300000 |  |  |  | *£2,046,720 identified in Southern sites S106’s- the majority of the land required. | Medium 2023-2028
Plus land requirement
Negotiations regarding Severn Trent land underway.
GI2 | Kenilworth / Crackley Country Park | Country Park to the north of Kenilworth. Mitigation for HS2 proposals. Potential to link with future any proposals for University of Warwick. Include pedestrian and cycle access, links to wider countryside, and ecological areas. | 2 | 2800000 |  | 2800000 |  | 2800000 |  |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period. | Long 2029 and beyond
Costs include maintenance and management for 13 years
GI3 | Arden Landscape Enhancement | Enhancements to Hay Wood, hedgerows, enhancement of historic parkland at Wroxall Abbey, improved access, new wetland and heathland habitats. Costs include maintenance and management for 13 years | 2 | 2670000 | 2670000 |  |  | 2670000 |  |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period | Long 2029 and beyond
| Whitely South | Provision of a country park | [9 empty] | To be delivered within arrangements related to planning permission. | Medium 2023-2028
GI4 | River Leam Tree Planting | New tree planting opportunities, enhancement of river environment, improved access. Will assist with flood alleviation. Costs include maintenance and management for 13 years | 2 | 4630000 | 4630000 |  |  | 4630000 |  |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period | Long 2029 and beyond
GI5 | Biodiversity Maintenance |  |  | To be quantified | [7 empty] | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period | Long 2029 and beyond
| Green Infrastructure Total |  |  | 12400000 | 7300000 | 5100000 |  | 12400000
| Open Space |  | A fuller assessment of the financial implications / requirements for open spaces will be forthcoming (June/July 2017) and will also embrace the additional housing / consequence of the modifications to the Local Plan. The PPM (preventative plan maintenance) study will inform a review/ refresh of the financial implications for open spaces.
GI6 | Improvements to Destination and District scale parks | Improvements to the District parks which have a key strategic role in the provision of open space in the District. This includes footpath improvements | 1 | 3100000 | 3100000 |  |  | 3100000 |  |  |  | *£730,994 set out in Southern sites S106’s thus far
GI7 | Neighbourhood and Local Green Spaces | Provision of new open space, play areas, allotments and other local green infrastructure (and enhancements of existing) in line with the Green Space Supplementary Planning Guidance. To be specified in planning applications | 1 | 2000000 |  | 2000000 |  | 2000000 |  |  |  | *Being specified in planning applications - £140,000 for play equipment in Southern sites S106’S thus far
GI8 | Open Space Maintenance | Maintenance agreements to cover costs for 13 years. | 1 | [8 empty] | *Normally calculated at point the open space is adopted using formula x 13 years
GI9 | Footpath connections | Enhance links in to countryside from new developments and beyond. To be specified in planning applications |  | 150000 |  | 150000 |  | 150000 |  |  |  | Public rights of way enhancement at the Asps
| OPEN SPACES TOTAL |  |  | 5250000 | 3100000 | 2150000 |  | 5250000
Playing Pitches
|  |  | It is intended that reviews of the Sports Pitches Strategy will take place throughout the Local Plan period (involving representatives of the National Governing Bodies of the main sports). This will review and refresh this data set. A review is anticipated in 2018/2019 | [8 empty] | *£408,000 set out in Southern sites S106’s for outdoor sports facilities thus far
Asps:-
3 new sports pitches to be provided on site
£25,650 to come from Gallows Hill for outdoor playing facilities pitches (resurfacing St Nicholas Park artificial pitch).
GI | Football Pitches | Requirement for 5 additional full size pitches and 4 mini pitches across the District |  | 1590000 | 1200000 | 390000 |  | 1590000 |  |  |  |  | Medium 2023-2028
10
GI | Cricket Pitches | Expansion of club infrastructure to increase adult cricket by 5 teams and 9 additional junior teams |  | 725000 | 650000 | £75,000 |  | 725000 |  |  |  |  | Medium 2023-2028
11
GI | Rugby Pitches | Expansion of club infrastructure to accommodate additional adult team, 3 additional junior teams and 3 additional midi team |  | 870000 | 750000 | £120,000 |  | 870000 |  |  |  |  | Medium 2023-2028
12
GI | Hockey Pitches | Additional demand for hockey by 5 teams, which could be accommodated on existing stock. However, the stock of artificial grass pitches will need renewing during the plan period. |  | 600000 | 550000 | £50,0000 |  | 600000 |  |  |  |  | Medium 2023-2028
13
| Playing Pitches Sub Total |  |  | 3785000 | 3150000 | 635000 |  | 3785000
Monitoring Fees
M1 | S106 and CIL Monitoring | Resource to manage and monitor Section.106 and CIL for10 years |  | 750000 |  | 750000 |  | 750000 |  |  |  | *£261,000 in Southern sites S106’s thus far
| Monitoring - Sub Heading |  |  | 750000 |  | 750000 |  | 750000
| TOTAL |  |  | 315015000 | 60950000 | 92337000 | 25757000 | 179044000 | 58697000 |  | 35300000