## Totals
Infrastructure Type / Project | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  |  | Funding secured
|  | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding | Total funding | Funding gap | CIL | S106 agreed | S106 recd | S278 | Committed Funding | Total
Transport Infrastructure Total | 109500000 | 16200000 | 29143000 | 25757000 | 71100000 | 29700000 | 3300000 | 104100000 | -5400000 | 0 | 19693566 | 1341000 | 0 | 29700000 | 50734566
Utilities Total | 575000 | 460000 | 0 | 0 | 460000 | 115000 | 0 | 575000 | 0 |  |  |  |  | 115000 | 115000
Education Total | 72660000 | 5040000 | 42900000 | 0 | 47940000 | 20000 | 0 | 47960000 | -24700000 |  |  |  |  | 20000 | 20000
Health Total | 67690000 | 12900000 | 7254000 | 0 | 20154000 | 12536000 | 31000000 | 63690000 | -4000000 |  |  |  |  | 12536000 | 12536000
Emergency Services Total | 2350000 | 1000000 | 1350000 | 0 | 2350000 | 0 | 0 | 2350000 | 0 |  |  |  |  | 0 | 0
Indoor Sports Total | 28590000 | 5200000 | 1547000 | 0 | 6747000 | 2000000 | 0 | 8747000 | -19843000 |  |  |  |  | 2000000 | 2000000
Cultural Facilities Total | 5355000 | 4200000 | 155000 | 0 | 4355000 | 0 | 1000000 | 5355000 | 0 |  |  |  |  | 0 | 0
Green Infrastructure Total | 12400000 | 7300000 | 5100000 | 0 | 12400000 | 0 | 0 | 12400000 | 0 |  |  |  |  | 0 | 0
Open Spaces Total | 5250000 | 3100000 | 2150000 | 0 | 5250000 | 0 | 0 | 5250000 | 0 |  |  |  |  | 0 | 0
Playing Pitches Total | 3785000 | 3150000 | 635000 | 0 | 3785000 | 0 | 0 | 3785000 | 0 |  |  |  |  | 0 | 0
Community Facilities Total | 4800000 | 2400000 | 2400000 | 0 | 4800000 | 250000 |  | 5050000 | 250000 |  |  |  |  | 250000 | 250000
Monitoring Total | 750000 | 0 | 750000 | 0 | 750000 | 0 | 0 | 750000 | 0 |  |  |  |  | 0 | 0
IDP Total | 313705000 | 60950000 | 93384000 | 25757000 | 180091000 | 44621000 | 35300000 | 260012000 | -53693000 | 0 | 19693566 | 1341000 | 0 | 44621000 | 65655566
|  |  |  | Check Total | 180091000

## Totals 2017-22
Infrastructure Type / Project | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  |  | Funding secured
|  | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding | Total funding | Funding gap | CIL | S106 agreed | S106 recd | S278 | Other Committed Funding | Total
Transport & Utilities 2017-22 Total | 49204000 | 5000000 | 17800000 | 19904000 | 42704000 | 7100000 | 3000000 | 52804000 | 3600000 | 0 | 7909390 | 0 | 0 | 7100000 | 15009390
Education 2017-22 Total | 62260000 | 2540000 | 29100000 | 0 | 31640000 | 20000 | 0 | 31660000 | -30600000 |  |  |  |  | 0 | 0
Health & Emergency Services 2017-22 Total | 64115000 | 12500000 | 4115000 | 0 | 16615000 | 12500000 | 31000000 | 60115000 | -4000000 |  |  |  |  | 0 | 0
Indoor Sports & Culture 2017-2022 Total | 28590000 | 5200000 | 1547000 | 0 | 6747000 | 2000000 | 13261000 | 22008000 | -6582000 |  |  |  |  | 0 | 0
Open Spaces & Sports Pitches 2017-2022 Total | 2300000 | 0 | 2300000 | 0 | 2300000 | 0 | 0 | 2300000 | 0 |  |  |  |  | 0 | 0
Community Facilities & Monitoring 2017-2022 Total | 1200000 | 1200000 | 0 | 0 | 1200000 | 250000 | 0 | 1450000 | 250000 |  |  |  |  | 0 | 0
0
IDP Total 2017-2022 | 207669000 | 26440000 | 54862000 | 19904000 | 101206000 | 21870000 | 47261000 | 170337000 | -37332000 | 0 | 7909390 | 0 | 0 | 7100000 | 15009390
|  |  |  | Check Total | 101206000

## Transport & Utilities
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Funding secured |  |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding |  | Other Potential Funding | CIL agreed | S106 agreed | S106 Rec'd | S278 agreed
PHYSICAL INFRASTRUCTURE
Transport: Sustainable Travel Infrastructure (Non Corridor specific)
T1 | Smarter Choices | Implementation of a range of behavioural measures such as workplace travel plans, sustainable transport packages for new residents, travel awareness campaigns, public transport information, car clubs and car sharing and teleworking, home working and home shopping. | 1 | 1000000 |  | 1000000 |  | 1000000 |  |  |  |  | 111176 |  |  | *Travel pack monies agreed in S106 from Southern sites is £350,000 thus far. | Early 2017-2022 and onwards throughout plan period
Transport Infrastructure: A452 Europa Way Corridor
T2 | Refer to appendix A that itemises the infrastructure components that are required for this corridor. | Major carriageway and junction improvements (including pedestrian and cycleway provision / connectivity). Includes Europa Way Corridor parts 1 and 2, Europa , Myton Road Roundabout, Shires Retail Park Roundabout, Grey's Mallory Roundabout. | 1 | 37000000 |  | 17500000 | 18700000 | 36200000 | 3600000 | Growth Deal bid secured. | £3,000,000 potentially from strategic development proposals in Stratford District |  | 7369390 |  |  | A project board has been convened to ensure that the phased development of the Corridor is co-ordinated, effective and minimises disruption. First phase of the works are the access works to Gallows Hill and Heathcote Farm developments funded through S278. This is likely to last 10 months Phase 2 is scheduled to be works related to the Catesby scheme, again funded through S278. | Early 2017-2022
Transport Infrastructure: A452 Leamington to Kenilworth Corridor
T3 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Includes carriageway and junction improvements as well as the provision of a park and ride facility and cycle route enhancements K2L. Includes cost of dualling of A452. |  | 17900000 |  | 6000000 |  | 6000000 |  |  | Highways England , RIS2 and future potential from S278 |  |  |  |  | . | Medium 2023-2027
T3a |  | Cycle and Bus Priority Measures for the A452 Corridor (Kenilworth to Leamington) |  | 1000000 | 1000000 |  |  | 1000000
T17 |  | North Leamington Park and ride |  | 1500000 | 1500000 |  |  | 1500000 | [8 empty] | TBC
Transport Infrastructure: Warwick-Leamington-Lillington (via Emscote Road)
T4 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Multi modal improvements Includes carriageway improvements and junction improvements to the following : Emscote Rd / Greville Road, Princess Drive/ Warwick New Road, A445/ Lillington Avenue/ Lillington Road. |  | 1660000 | 1660000 |  |  | 1660000 |  |  | Emscote road works, Princes drive junction may be recipients of SEP bid finance | [5 empty] | Early to medium 2017-2027
Transport Infrastructure: Leamington South (including Tachbrook Road)
T5 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Multi modal improvements,Includes carriageway improvements and junction improvements to Princes Drive / Park Road, Bath Street Gyratory,Adelaide Road/ Avenue Road, Dormer Place/ Adelaide Road. |  | 3900000 | 3900000 |  |  | 3900000 |  |  | £120,000 from strategic development proposals in Stratford District |  |  |  |  | *Note- all items within this Locality to be subject to a WCC SEP bid for finance. | Early to medium 2017-2027
|  | Sydenham Drive / Radford Road potential widening |  | 653000 |  |  | 653000 | 653000
Transport Infrastructure: Warwick Town Centre to Heathcote via Gallows Hill
T6 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Includes carriageway improvements and junction improvements |  | 5200000 |  |  | 5200000 | 5200000 |  |  | £180,000 from strategic development in Stratford District |  | 3150000 |  |  |  | Medium 2023-2027
|  | Specific road improvements – (two lanes to both Banbury Road and Gallows Hill). | [5 empty] | 0
Transport Infrastructure: Warwick Town Centre to Leamington (via Myton Road)
T7 | Refer to appendix A that itemises the infrastructure components that are required for this corridor. | Myton Road Roundabout - synchronisation of signaling system |  | 1204000 |  |  | 1204000 | 1204000 |  |  | Potential for funding from SEP / Growth Deal Bid |  |  |  |  | Details in Europa Way and Warwick Town Centre to Heathcote via Gallows Hill corridors | Early 2017-2022
Transport Infrastructure: A429 Coventry Road, Warwick
T8 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Coventry Road / Spinney Hill Roundabout |  | 1140000 | 1140000 |  |  | 1140000 | [8 empty] | Medium 2023-2027
Transport Infrastructure: A425 Birmingham Road, Warwick
T9 | A46/A425/A4177 Birmingham Road ‘Stanks Island’ |  | 1 | 6000000 |  | 300000 |  | 300000 | 3500000 | from SEP |  |  | 540000 |  |  |  | Early 2017-2022
[8 empty] | 0 | 2600000 | from WCC Corporate Growth Fund
Transport Infrastructure: A46 to Cubbington
T10 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Bericote Rd / Stoneleigh Rd, Kenilworth Road /Westhill Roiad, A445/Sandy Lane |  | 2338000 |  | 2338000 |  | 2338000 | [7 empty] | Confirmation of assignation to CIL / S106 yet to be confimed by County Highways | ??
Transport Infrastructure: Strategic corridor improvements
T11 | M40 Motorway Traffic Management and A46 Expressway Upgrade to improve linkages with M5 and M6 | Provision of Smart Motorways between J14 and J15 of the M40 |  | n/a |  |  |  | 0 |  |  | S106 contributions from strategic development in Stratford District |  |  |  |  | The Local Plan evidence base highlights that WDC Local Plan growth is not the trigger for major improvements to the strategic motorway network. These capacity concerns will have to be addressed before the end of the Plan period. The precise identification and costing of any improvements is yet to be determined and there is potential for any scheme(s) to be predominantly financed / delivered by HE/ DfT | Late 2028 and beyond
Transport Infrastructure: Kenilworth Locality Improvements
T12 | Refer to appendix A that itemises the infrastructure component s that are required for this corridor. | Including improvements to Kenilworth Gyratory,A45/ Kenilworth Road,A429 / Stoneleigh Road/ Gibbett Hill Road. |  | 503000 |  | 503000 |  | 503000 | [7 empty] | Note nominal contribution to A45/ Kenilworth Road and A429 Stoneleigh Road/ Gibbet Hill Road yet to be identified | Early to medium 2017-2027
T12a |  | Stoneleigh Road / A46/ Dalehouse Ln/ Stoneleigh Rd |  | 20000000 |  |  |  |  | 20000000 | growth deal | [5 empty] | Dft funding transferred from A45/ A429
Transport Infrastructure: Sub-regional Employment Site
T14 | Transport Infrastructure Associated with Sub-regional employment site | The recently approved planning application at Whitely South incorporates the delivery of the infrastructure set out below. | [5 empty] | 0 | [7 empty] | It should be noted that the South of Whitely application does not cover the total that is allocated in the Local Plan for employment purposes and further requirements (and consequently additional contributions may be sought / forthcoming). | Early 2017-2022
|  | • New junction on A45 between Festival and Toll Bar islands including bridge over A45 to link site with Jaguar Whitley Business Park (Coventry) | [5 empty] | 0
|  | • New access road within the site to link the two zones (east of Baginton and south of Middlemarch Business Park). | [5 empty] | 0
|  | • New roads within the Jaguar Whitley Business Park (Coventry) | [5 empty] | 0
|  | • Improvements to capacity of Festival island (Coventry) and the A46/Stoneleigh Road junction | [5 empty] | 0
|  | • Enhancement to Stivichall bypass/London Road bypass junction | [5 empty] | 0
|  | • New roundabout at junction of Bubbenhall and Stoneleigh Roads. | [5 empty] | 0
|  | • New bus route with high quality infrastructure and frequent services between Coventry City Centre and site. | [5 empty] | 0
|  | • Extensive improvements to off-site footpaths and cycleway links. | [5 empty] | 0
|  | • Measures to restrict traffic from the site entering/exiting along Rowley Road/Bubbenhall Road. | [5 empty] | 0
Transport Infrastructure: Town Centre Strategies
T15a |  | Town Centre Strategies, Leamington Spa, Warwick, Kenilworth | 1 | 5000000 | 5000000 |  |  | 5000000 | [7 empty] | £2 M Leamington Spa, £2M Warwick, £1M Kenilworth | Early 2017-2022
T15b |  | Castle Hill Gyratory Signals |  | 876000 |  | 876000 |  | 876000
T15c |  | Improvements to Priory Road Smith Street and St Nicholas Church Street |  | 626000 |  | 626000 |  | 626000
T16 | Cycling,bus priority measures and other sustainable transport schemes not specified in Appendix B of the 2016 STA |  |  | 2000000 | 2000000 |  |  | 2000000
T99 | Strategic, non-specific infrastructure contributions | [11 empty] | 8523000 | 1341000
| Transport Infrastructure Total |  |  | 109500000 | 16200000 | 29143000 | 25757000 | 71100000 | 29700000 |  | 3300000 | 0 | 19693566 | 1341000 | 0
| Telecommunications | [14 empty] | Refer to appendix 1
| Utilities: Electric and Gas | [14 empty] | Refer to appendix 1
| Utilities: Water and Sewage | [14 empty] | Refer to Appendix 1
Utilities: Waste
W1 | Household Waste and Recycling | Redesign of existing household recycling facilities to accommodate population increase. | 2 | 575000 | 460000 |  |  | 460000 | 115000 | [7 empty] | Medium 2023-2027
| Waste: Sub Total |  |  | 575000 | 460000 | 0 | 0 | 460000 | 115000 |  | 0
| Utilities Total |  |  | 575000 | 460000 | 0 | 0 | 460000 | 115000 |  | 0

## Transport & Utilities 2017 - 22
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Funding secured |  |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding |  | Other Potential Funding | CIL agreed | S106 agreed | S106 Rec'd | S278 agreed
T2 | Refer to appendix A that itemises the infrastructure components that are required for this corridor. | Major carriageway and junction improvements (including pedestrian and cycleway provision / connectivity). Includes Europa Way Corridor parts 1 and 2, Europa , Myton Road Roundabout, Shires Retail Park Roundabout, Grey's Mallory Roundabout. | 1 | 37000000 | 0 | 17500000 | 18700000 | 36200000 | 3600000 | Growth Deal bid secured. | £3,000,000 potentially from strategic development proposals in Stratford District |  | 7369390 |  |  | A project board has been convened to ensure that the phased development of the Corridor is co-ordinated, effective and minimises disruption. First phase of the works are the access works to Gallows Hill and Heathcote Farm developments funded through S278. This is likely to last 10 months Phase 2 is scheduled to be works related to the Catesby scheme, again funded through S278. | Early 2017-2022
T7 | Refer to appendix A that itemises the infrastructure components that are required for this corridor. | Myton Road Roundabout - synchronisation of signaling system |  | 1204000 | 0 | 0 | 1204000 | 1204000 |  |  | Potential for funding from SEP / Growth Deal Bid |  |  |  |  | Details in Europa Way and Warwick Town Centre to Heathcote via Gallows Hill corridors | Early 2017-2022
T9 | A46/A425/A4177 Birmingham Road ‘Stanks Island’ |  | 1 | 6000000 | 0 | 300000 | 0 | 300000 | 3500000 | from SEP |  |  | 540000 |  |  |  | Early 2017-2022
T14 | Transport Infrastructure Associated with Sub-regional employment site | The recently approved planning application at Whitely South incorporates the delivery of the infrastructure set out below. | [13 empty] | It should be noted that the South of Whitely application does not cover the total that is allocated in the Local Plan for employment purposes and further requirements (and consequently additional contributions may be sought / forthcoming). | Early 2017-2022
T15a |  | Town Centre Strategies, Leamington Spa, Warwick, Kenilworth | 1 | 5000000 | 5000000 | 0 | 0 | 5000000 | [7 empty] | £2 M Leamington Spa, £2M Warwick, £1M Kenilworth | Early 2017-2022
| Transport & Utilities 2017-22 Total |  |  | 49204000 | 5000000 | 17800000 | 19904000 | 42704000 | 7100000 |  | 3000000 | 0 | 7909390 | 0 | 0

## Education
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  | Funding secured |  |  |  | Update and Progress - September 2017 | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding | CIL agreed | S106 agreed | S106 Rec'd | S278 agreed
SOCIAL INFRASTRUCTURE
Education: Primary Schools
E1a | New Primary Schools | Heathcote Primary School (1 x 2 form) | 1 | 3500000 |  | 3500000 |  | 3500000 | Forward funded by WCC in advance of S106 receipts – school to be a free school academy run by the Community Academies Trust. | [5 empty] | The school has opened to pupils September 2017. Initially opening at 1 form of entry but will expand to 2FE when demand requires. Currently admitting in Year 1 and Reception. There is a private provider day care facility on site (Polka Dot) The build has been forward funded by WCC in advance of S106 income receipt. The school will be sponsored by The Communities Academy Trust which currently manages a number of schools in Warwickshire and Staffordshire. Locally the Trust sponsor Woodloes Primary School | Early 2017-2022
E1b | New Primary Schools | Grove Farm (Oakley Grove) Primary School (1 x 1 form) | 1 | £3.400,000 |  | 3400000 |  | 3400000 |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. |  |  |  |  | Current Government Policy means that this school will be delivered as a Free School. Land will be available to support the provision of a 2 form entry primary school. The school will only be brought forward when demand dictates. | Medium 2023-2027
E1c | New Primary Schools | Myton / West of Europa Way (1 x 2 form) | 1 | 6000000 |  | 6000000 |  | 6000000 |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. Assumed existing S106 contributions will cover this |  | 1693530 |  |  | *Location to be adjacent Myton School details being developed through master planning arrangements. Exact location yet to be determined | Medium 2023-2027
E1d | New Primary Schools | Whitnash East / South Sydenham (1x 1 form) | 1 |  |  |  |  | 0 |  | Will be funded as a free school if required |  |  |  |  | This site will only be brought forward if demand requires. Potential issues re access to site. Linked to purchase of land currently occupied by Campion School. Planning application not yet submitted so no secured site linked with a planning permission and associated S106 agreement | Late 2028 and beyond
E1e | New Primary Schools | Thickthorn school (1x1 form) - located at Thickthorn. | 1 | 6000000 |  | 6000000 |  | 6000000 |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. |  |  |  |  | Originally WCC were looking at two x 1 form entry primary schools. This would have seen one school capacable of admitting up to 210 pupils at Thickthorn and a second school of the same size elsewhere within the growth area of Kenilowrth, possibly at Southcreast Farm The new school (s) would be free schools and the Education Funding Agency are not supportive of 1FE schools. Thought will now need to be refocussed to the provision of one x 2FE primary school within the Kenilworth growth area. There is minimal spare capacity within Kenilworth primary schools so a new school will be required early in the housing delivery phase. | Early 2017-2022
E1f | New primary Schools | Kings Hill Allocation - (based on 2000 dwellings) 1x 2 form entries. Note: Education planning requires consideration for requirements across the entire proposed site i.e. 4000 dwellings and discussions with developers have been on this basis) | [5 empty] | 0 | [6 empty] | Estimated pupil yield for 4000 dwellings suggests the need for up to 5 forms of entry at primary school age. The pattern of provision is still to be determined although The proposed primary eductaion solution for Kings Hill is for the provision of 2 x 2FE primary schools with one of those schools on a site capacble of expansion to 3FE if required. Discussions have taken place with Coventry City Council to ensure we don’t over provide places and put existing schools at risk. Discussions have confirmed that there is no surplus capacity of school places in the neighbouring part of Coventry. Pre-app discussions contunue to help inform master planning. New primary school provision will be required reasonably early on in development. | Early 2017-2022
E1g | New Primary Schools (Asps) | Asps’ obligation reserves land for a primary school, one form entry plus pre-school; 1.1 acres and primary school funding package. |  | 2900000 |  | 2900000 |  | 2900000 |  | Any additional costs to be funded by the EFA. |  | 2723067 |  |  | No further action will be taken until a Reserved Matters application is submitted. Agreement about the location of the school site will be required. Masterplan discussions underway - early stages | Medium 2023-2027
E2a | Expansion of existing schools (Whitnash) | Whitnash Primary School – 0.5 form entry additional capacity | 1 | 1500000 |  | 1500000 |  | 1500000 | [6 empty] | The school is now admitting up to 2 Forms of entry on an informal basis when demand is required. It is still planned to formally expand the school moving forward but this is currently on hold. | Early 2017-2022
E2b | Expansion of existing school (Barford) | Development of additional capacity at Barford Primary School | 1 | 500000 |  | 480000 |  | 480000 | 20000 |  |  | 93496 |  |  | WCC worked with the Coventry Diocesan Board of Education to enable St Peter's to admit up to 1 form of entry throughout the school. The build delivered by the DBE but funded by WCC in advance of S106 receipt. | Early 2017-2022
E2c | Expansion of existing school (Budbrooke) | Budbrooke to be expanded from 1.5 form entry to 2 form entry to cater for additional demand in respect of new allocations in the vicinity(Hampton Magna / Hatton Park) |  | 1500000 |  | 1500000 |  | 1500000 | [6 empty] | Budbrooke Primary School is now managed by the Community Academies Trust. Budbrooke Primary is on a large enough site to support expansion to 2 forms of entry. Expansion will only be considered once there is a recognised need. This is to ensure sustainability. Expansion will not be required until growth in housing locally. | Medium 2023-2027
E3 | Village schools | No additional requirement. The provision of additional capacity as set out in E1, E2 and E3, combined with displacing children out of priority area means that the proposals for new development in villages can be met at the following schools: | [12 empty] | Cubbington, Radford Semele and Lapworth Schools don't lend themselves to expansion. Bishops Tachbrook possibly could expand but the grwoth locally would not support an additional form of entry. All Saints Primary School at Leek Wootton have expressed an interest in expansion. Proposed growth locally does not require expansion and any potential S106 income would be unlikely to support the cost of the required build. A number of existing S106s require funds towards the provision of additional school places as a contribution towards the cost of home to school transport. This is in recognition that the local schools can't be expanded and so children will have to travel out of the area to access a school place. | Late 2028 and beyond
• Bishops Tachbrook
• Cubbington
• Budbrooke
• Lapworth
• Radford Semele
• Burton Green
• All Saint’s Leek Wootton
| Primary Schools - Sub Total |  |  | 21900000 | 0 | 25280000 | 0 | 25280000 | 20000 |  | 0 | 4510093 | 0 | 0
Education: Secondary Schools
| South of Warwick Sites (overview) | [6 empty] | 0 | [6 empty] | The delivery of additional secondary school places will be delivered through a phased approach. The first phase will see the expansion of Campion School and discussions are taking place between the Academy and the Local Authority. Phase 2 is likely to see the provision of a new free school on reserved land. We are aware that The Trinity School has expressed an interest in changing their existing offer and this will be a consideration. The first phase of provision of new secondary school places will be through the first expansion of Campion School. Initial discussions continue with the school and additional places should be available from September 2019.
E4 | South of Warwick: Southern Sites | See above | 1 | To be quantified |  |  |  | 0 | [6 empty] | The exact delivery of additional places is still to be determined. Any new school will be a free school as per current Government policy. Additional provision at this location forms part of the wider strategy for ensuring a sufficient supply of school places. | Medium 2023-2027
E5 | Whitnash East | Expansion of Campion School | 1 | 8150000 |  | 8150000 |  | 8150000 |  |  |  | 623330 |  |  | First phase expansion due by 2019 | Early 2017-2022
E6 | Kenilworth | There is an aspiration for Kenilworth School to relocate both of the existing school sites on to one new site at Southcrest farm. | 1 | 38200000 |  | 7600000 |  | 7600000 |  | Note: - A significant contribution may come from existing school site land sales. |  |  |  |  | Development of an all through (11-18) Kenilworth School in place of the current split site Kenilworth School should not solely be funded by Developer contributions as the scheme is not the result of increased pupil numbers. The proposed growth within Kenilworth Town requires the need for expansion of provision at Kenilworth School. The proposed development at Kings Hill will require its own secondary provision. Discussions contnue around the reloaction and expansion of Kenilworth School. | Early 2017-2022
E7 | Kings Hill Allocation | As site proceeds to 4000 dwelling capacity (beyond plan period /2000 threshold) land should be reserved to cover the possibility of a new ‘all-through’ primary / secondary school and Special Educational needs facilities. |  | To be quantified |  |  |  | 0 | [6 empty] | The provision of 4,000 homes will require a minimum of 5 form of entry for education purposes. Proposed development at Westwood Heath will also require the provision of additional capacity and this could see the need for 6 or 7 forms of entry in total at secondary age. Discussions are taking place with the developers but the need for on-site secondary provision is agreed. Provision will need to be funded from developer contributions and possible forward funding from EFA as part of the provision of free schools. It is likely that the new school will also support the provision of school places for growth in the Westwood Heath area. On-going pre app discussions continue with all interested parties. | Medium 2023-2027
E8 | North of Milverton / Blackdown / Stoneleigh Road allocations | Expansion of existing school provision, possibly North Leamington and / or The Trinity School |  | To be quantified |  |  |  | 0 | [6 empty] | Situation to be kept under review as growth in the area unfolds | Late 2028 and beyond
E9 | Other Sites | Unspecified expansion to primary and secondary schools | 2 | £2,500,000 | 2500000 |  |  | 2500000 |  |  |  | 4875471 |  |  | Situation to be kept under review as growth in the area unfolds | Medium 2023-2027
| Secondary Schools Sub Total |  |  | 46350000 | 2500000 | 15750000 | 0 | 18250000 |  |  | 0 | 5498801 | 0 | 0
Education : 0-5 Provision
E10 | District-wide facilities | Contribution to improvement and expansion of existing facilities – details to be confirmed | 2 | 1200000 | 1200000 |  |  | 1200000 |  |  |  | 444103 |  |  | It is the aspiration of WCC that all new primary schools will have pre-school provision on site, either run by the school itself or by a private provider. This cannot be guaranteed however as the Free Schools agenda rolls out and WCC have less control. WCC will continue to seek pre-school contributions from developers to ensure a sufficient supply of pre-school provision. | Early 2017 onwards
Education: Special Educational Needs Provision
E11 | District-wide facilities | Contribution to improvement and expansion of existing facilities – details to be confirmed | 1 | 1340000 | 1340000 |  |  | 1340000 |  |  |  | 186835 | 18436 |  | Funds collected to support necessary adaptations to enable pupils to attend schools of their choice as identified in their Education Health and Care Plan. This is likley to see adaptations to mainstream schools rather than necessarily expansion of existing special schools. | Early 2017 onwards
School Transport
E12 | Contribution to school transport |  |  | 1870000 |  | 1870000 |  | 1870000 | [6 empty] | WCC will continue to seek contributions towards the provision of school transport where believed to be justifiable. This could be because it is not possible to expand the local primary school or because pupils have to travel more than the statutory distance to secure secondary places. | Medium 2023-2027
| Education Other : Sub Total |  |  | 4410000 | 2540000 | 1870000 | 0 | 4410000 | 0 |  | 0 | 630938 | 18436 | 0
| Education Total |  |  | 72660000 | 5040000 | 42900000 | 0 | 47940000 | 20000 |  | 0 | 10639832 | 18436 | 0

## Education 2017 - 2022
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  | Update and Progress - September 2017 | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding
E1a | New Primary Schools | Heathcote Primary School (1 x 2 form) | 1 | 3500000 | 0 | 3500000 | 0 | 3500000 | Forward funded by WCC in advance of S106 receipts – school to be a free school academy run by the Community Academies Trust. |  | The school has opened to pupils September 2017. Initially opening at 1 form of entry but will expand to 2FE when demand requires. Currently admitting in Year 1 and Reception. There is a private provider day care facility on site (Polka Dot) The build has been forward funded by WCC in advance of S106 income receipt. The school will be sponsored by The Communities Academy Trust which currently manages a number of schools in Warwickshire and Staffordshire. Locally the Trust sponsor Woodloes Primary School | Early 2017- 2022
E1e | New Primary Schools | Thickthorn school (1x1 form) - located at Thickthorn. | 1 | 6000000 | 0 | 6000000 | 0 | 6000000 |  | Expect this to be provided as part of the Free School initiative. Probable forward funding by the Education Funding Agency. | Originally WCC were looking at two x 1 form entry primary schools. This would have seen one school capacable of admitting up to 210 pupils at Thickthorn and a second school of the same size elsewhere within the growth area of Kenilowrth, possibly at Southcreast Farm The new school (s) would be free schools and the Education Funding Agency are not supportive of 1FE schools. Thought will now need to be refocussed to the provision of one x 2FE primary school within the Kenilworth growth area. There is minimal spare capacity within Kenilworth primary schools so a new school will be required early in the housing delivery phase. | Early 2017-2022
E1f | New primary Schools | Kings Hill Allocation - (based on 2000 dwellings) 1x 2 form entries. Note: Education planning requires consideration for requirements across the entire proposed site i.e. 4000 dwellings and discussions with developers have been on this basis) |  | 0 | 0 | 0 | 0 | 0 |  |  | Estimated pupil yield for 4000 dwellings suggests the need for up to 5 forms of entry at primary school age. The pattern of provision is still to be determined although The proposed primary eductaion solution for Kings Hill is for the provision of 2 x 2FE primary schools with one of those schools on a site capacble of expansion to 3FE if required. Discussions have taken place with Coventry City Council to ensure we don’t over provide places and put existing schools at risk. Discussions have confirmed that there is no surplus capacity of school places in the neighbouring part of Coventry. Pre-app discussions contunue to help inform master planning. New primary school provision will be required reasonably early on in development. | Early 2017-2022
E2a | Expansion of existing schools (Whitnash) | Whitnash Primary School – 0.5 form entry additional capacity | 1 | 1500000 | 0 | 1500000 | 0 | 1500000 |  |  | The school is now admitting up to 2 Forms of entry on an informal basis when demand is required. It is still planned to formally expand the school moving forward but this is currently on hold. | Early 2017-2022
E2b | Expansion of existing school (Barford) | Development of additional capacity at Barford Primary School | 1 | 500000 | 0 | 480000 | 0 | 480000 | 20000 |  | WCC worked with the Coventry Diocesan Board of Education to enable St Peter's to admit up to 1 form of entry throughout the school. The build delivered by the DBE but funded by WCC in advance of S106 receipt. | Early 2017-2022
E5 | Whitnash East | Expansion of Campion School | 1 | 8150000 | 0 | 8150000 | 0 | 8150000 |  |  | First phase expansion due by 2019 | Early 2017-2022
E6 | Kenilworth | There is an aspiration for Kenilworth School to relocate both of the existing school sites on to one new site at Southcrest farm. | 1 | 38200000 | 0 | 7600000 | 0 | 7600000 |  | Note: - A significant contribution may come from existing school site land sales. | Development of an all through (11-18) Kenilworth School in place of the current split site Kenilworth School should not solely be funded by Developer contributions as the scheme is not the result of increased pupil numbers. The proposed growth within Kenilworth Town requires the need for expansion of provision at Kenilworth School. The proposed development at Kings Hill will require its own secondary provision. Discussions contnue around the reloaction and expansion of Kenilworth School. | Early 2017-2022
| Education Other : Sub Total |  |  | 4410000 | 2540000 | 1870000 | 0 | 4410000 | 0
|  | Education 2017-22 Total |  | 62260000 | 2540000 | 29100000 | 0 | 31640000 | 20000

## Health & Emerg Serv
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding |  | Other Potential Funding
Health: Acute and Community Health Services
H1 | Warwick Hospital | First ward block at the Warwick Hospital site – the main provider of acute hospital services. | 1 | 12000000 |  | 4000000 |  | 4000000 |  |  | 4000000 | *Delivered but forward funded – money recouped from WDC/SDC developer contributions. £6,000,000 overall available from S106 agreements in Warwick District thus far £977,000 to go to acute healthcare from the Asps Gallows Hill will deliver £476,550 for acute healthcare provision Note above figures are incorporated in the overall WDC S106 total | Early 2017-2022
H2 | Warwick Hospital | Additional outpatient, diagnostic, treatment and in-patient facilities, including hubs for community health care teams at Warwick and Stratford Hospitals - it is recognised that the first New Ward Block and Stratford Hospital projects will not fully meet the healthcare demand associated with the new population growth projections and we will require additional infrastructure to deliver future acute and community healthcare requirements on a sustainable basis | 2 | 12000000 | 4000000 |  |  | 4000000 | 4000000 | SDC | 4000000 |  | Early 2017-2022
H3 | Stratford Hospital | A new hospital at our Stratford Hospital site including outpatient, diagnostic, treatment and inpatient facilities and a hub for community healthcare teams. (Target completion for Phase 1 by Autumn 2015).This is integral to enabling additional capacity at Warwick Hospital |  | 40000000 | 8500000 |  |  | 8500000 | 8500000 | SDC | 23000000 | Development underway –anticipated completion 2017 CIL apportionment to be shared with Stratford District Council | Early 2017-2022
| Health – Hospital Sub Total |  |  | 64000000 | 12500000 | 4000000 | 0 | 16500000 | 12500000 |  | 31000000
Health: GP Services
H4 | Warwick: Southern Sites | A new 5 GP medical centre to be provided land at Myton/ West of Europa Way | 1 | 2900000 |  | 2900000 |  | 2900000 |  |  |  | *Site being identified through detailed through detailed planning negotiations. | Medium 2023-2027
H5 | Warwick Gates medical centre | Expansion / additional works to improve existing medical centre |  | 115000 |  | 115000 |  | 115000 |  |  |  | Note £113,000 of S106 finance will fund these additional works to the existing surgery at Warwick Gates | Early 2017-2022
H6 | Kenilworth | Expanded medical facilities to meet the needs of additional development. | 1 | 140000 |  | 126000 |  | 126000 | 14000 |  |  |  | TBC
H7 | Whitnash / Sydenham / Radford Semele | Expansion of existing medical centre - potentially Croft Medical Centre | 1 | 95000 |  | 73000 |  | 73000 | 22000 |  |  |  | TBC
H8 | Lillington / Cubbington | Extension to Cubbington Road Surgery | 1 | 40000 |  | 40000 |  | 40000 |  |  |  |  | TBC
H9 | Urban Sites | Combining of existing practices |  | 400000 | 400000 |  |  | 400000 |  |  |  |  | TBC
| Health - GP Sub Total |  |  | 3690000 | 400000 | 3254000 | 0 | 3654000 | 36000
| Health Total |  |  | 67690000 | 12900000 | 7254000 | 0 | 20154000 | 12536000 |  | 31000000
Emergency Services
ES1 | Police: Custody Suite | 12 additional cells needed | 2 | 500000 | 500000 |  |  | 500000
ES2a | Police: Safer Neighbourhood Team Police Office | Additional offices at Europa Way | 1 | 450000 |  | 450000 |  | 450000 |  |  |  |  | Medium 2023-2027
ES2b | Police: Safer Neighbourhood Team Police Office | Additional office at Lower Heathcote Farm |  | 450000 |  | 450000 |  | 450000 |  |  |  |  | Medium 2023-2027
ES2c | Police: Safer Neighbourhood Team Police Office | Additional office at Thickthorn |  | 450000 |  | 450000 |  | 450000 |  |  |  |  | Medium 2023-2027
ES2d | Police: Safer Neighbourhood Team Police Office at the Asps | Additional office at Asps plus £188,000 for fitting out etc to be delivered by developers (agreed in legal obligations) | [5 empty] | 0 | Additional office at Asps plus fitting out met in Asps obligation. |  |  |  | Medium 2023-2027
ES3 | Other police equipment and costs | A range of other “CIL Compliant” costs including vehicles, communications technology and surveillance equipment, training, uniform and personal equipment | 2 | 500000 | 500000 |  |  | 500000 |  |  |  |  | Medium 2023-2027
ES4 | Ambulance Service | The service has undertaken a recent premises review. They have no further premises requirements during the Plan Period | N/A | 0 |  |  |  | 0 |  |  |  | The Ambulance Trust is keen to work with Developers to support the provision of defibrillators. WCC supports requests for the provision of defibrillators on all new public buildings either through direct provision of the payment of a financial contribution. (Approx cost per defib is £1,500) | Medium 2023-2027
| Emergency Services Total |  |  | 2350000 | 1000000 | 1350000 | 0 | 2350000
Note on L4: alan: NHS
Note on L5: alan: NHS
Note on L6: alan: NHS

## Health & Emerg Serv 2017 - 2022
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding |  | Other Potential Funding
H1 | Warwick Hospital | First ward block at the Warwick Hospital site – the main provider of acute hospital services. | 1 | 12000000 | 0 | 4000000 | 0 | 4000000 | 0 |  | 4000000 | *Delivered but forward funded – money recouped from WDC/SDC developer contributions. £6,000,000 overall available from S106 agreements in Warwick District thus far £977,000 to go to acute healthcare from the Asps Gallows Hill will deliver £476,550 for acute healthcare provision Note above figures are incorporated in the overall WDC S106 total | Early 2017-2022
H2 | Warwick Hospital | Additional outpatient, diagnostic, treatment and in-patient facilities, including hubs for community health care teams at Warwick and Stratford Hospitals - it is recognised that the first New Ward Block and Stratford Hospital projects will not fully meet the healthcare demand associated with the new population growth projections and we will require additional infrastructure to deliver future acute and community healthcare requirements on a sustainable basis | 2 | 12000000 | 4000000 | 0 | 0 | 4000000 | 4000000 | SDC | 4000000 |  | Early 2017-2022
H3 | Stratford Hospital | A new hospital at our Stratford Hospital site including outpatient, diagnostic, treatment and inpatient facilities and a hub for community healthcare teams. (Target completion for Phase 1 by Autumn 2015).This is integral to enabling additional capacity at Warwick Hospital |  | 40000000 | 8500000 | 0 | 0 | 8500000 | 8500000 | SDC | 23000000 | Development underway –anticipated completion 2017 CIL apportionment to be shared with Stratford District Council | Early 2017-2022
H5 | Warwick Gates medical centre | Expansion / additional works to improve existing medical centre |  | 115000 |  | 115000 |  | 115000 |  |  |  | Note £113,000 of S106 finance will fund these additional works to the existing surgery at Warwick Gates | Early 2017-2022
| Health & Emergency Services 2017-22 Total |  |  | 64115000 | 12500000 | 4115000 | 0 | 16615000 | 12500000 |  | 31000000

## Indoor Sports & Cultural
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding |  | Other Potential Funding
Indoor Sports Facilities: Sports Halls and Swimming Pools
ISF1 | Improvements to sports hall and swimming pools | Phase1 (Newbold Comyn and St Nicholas centres)- £12,000,000 |  | 16590000 |  | 1329000 |  | 1329000 | 2000000 | 13261000 |  | First phase of works completed and refurbished Newbold Comyn open, St Nicholas imminent. Second phase due for completion in Spring 2018 | Early 2017-2022
|  | Phase 2 – (Abbey Fields / Castle Farm) |  | 12000000 | 5200000 | 218000 |  | 5418000 |  |  |  | Scoping for Phase 2 likely to start late 2017, until scoping completed costs are indicative only | Early 2017-2022
| Indoor Sports Total |  |  | 28590000 | 5200000 | 1547000 | 0 | 6747000 | 2000000 | 13261000
Cultural Facilities: Library Services
CU1 | Contributions to Library Service | IT and stock purchases to support growth in population. | 2 | 155000 |  | 155000 |  | 155000 |  |  |  | The County Council does not currently have plans to deliver new library provision. Financial contributions are requested for all new developments of more than 24 dwellings to ensure that the service is able to provide appropriate stock as well as delivering targeted promotions. | Medium 2023-2027
Cultural Facilities: Arts and Culture
CU2 | Kenilworth Public Service Centre and Community Theatre | Provide new public service centre along with a community theatre in line with the proposals consulted on for the Kenilworth Town Plan |  | 5200000 | 4200000 |  |  | 4200000 |  |  | £1,000,000 assumed from sale of current Talisman theatre site |  | Medium 2023-2027
| Cultural Facilities Total |  |  | 5355000 | 4200000 | 155000 |  | 4355000 |  |  | 1000000
Note on J5: alan: Sport England
Note on K5: alan: WDC Funding

## Indoor Sports & Cultur 2017-22
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding |  | Other Potential Funding
ISF1 | Improvements to sports hall and swimming pools | Phase1 (Newbold Comyn and St Nicholas centres)- £12,000,000 |  | 16590000 | 0 | 1329000 | 0 | 1329000 | 2000000 | 13261000 |  | First phase of works completed and refurbished Newbold Comyn open, St Nicholas imminent. Second phase due for completion in Spring 2018 | Early 2017-2022
|  | Phase 2 – (Abbey Fields / Castle Farm) |  | 12000000 | 5200000 | 218000 | 0 | 5418000 | 0 | 0 |  |  | Early 2017-2022
| Indoor Sports & Culture 2017-2022 Total |  |  | 28590000 | 5200000 | 1547000 | 0 | 6747000 | 2000000 | 13261000 | 0

## Open Spaces & Sports Pitches
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding
GREEN INFRASTRUCTURE
Country parks and Strategic Green Infrastructure
GI1 | Tach Brook Country Park | 62.5 hectare Country Park to north side of Tach Brook providing a separation and recreational space between Bishops Tachbrook and proposed new development to the south of Harbury Lane. Include pedestrian and cycle access, links to wider countryside, and ecological areas. Costs include maintenance and management for 13 years. | 1 | 2300000 |  | 2300000 |  | 2300000 |  |  | *£2,046,720 identified in Southern sites S106’s- the majority of the land required. Negotiations regarding Severn Trent land underway. Report due to November Executive regarding procurement of design consultant | Early 2017-2022
GI2 | Kenilworth / Crackley Country Park | Country Park to the north of Kenilworth. Mitigation for HS2 proposals. Potential to link with future any proposals for University of Warwick. Include pedestrian and cycle access, links to wider countryside, and ecological areas. Costs include maintenance and management for 13 years | 2 | 2800000 |  | 2800000 |  | 2800000 |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period. | Late 2028 and beyond
GI3 | Arden Landscape Enhancement | Enhancements to Hay Wood, hedgerows, enhancement of historic parkland at Wroxall Abbey, improved access, new wetland and heathland habitats. Costs include maintenance and management for 13 years | 2 | 2670000 | 2670000 |  |  | 2670000 |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period | Late 2028 and beyond
GI14 | Whitely South | Provision of a country park | [5 empty] | 0 |  |  | To be delivered within arrangements related to planning permission. | Medium 2023-2027
GI4 | River Leam Tree Planting | New tree planting opportunities, enhancement of river environment, improved access. Will assist with flood alleviation. Costs include maintenance and management for 13 years | 2 | 4630000 | 4630000 |  |  | 4630000 |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period | Late 2028 and beyond
GI5 | Biodiversity Maintenance |  |  | To be quantified |  |  |  | 0 |  |  | Delivery of this may be subject to prioritisation of available CIL resources later in the plan period | Late 2028 and beyond
| Green Infrastructure Total |  |  | 12400000 | 7300000 | 5100000 | 0 | 12400000
Open Space
GI6 | Improvements to Destination and District scale parks | Improvements to the District parks which have a key strategic role in the provision of open space in the District. This includes footpath improvements | 1 | 3100000 | 3100000 |  |  | 3100000 |  |  | *£730,994 set out in Southern sites S106’s thus far | Early to medium 2017-2027
GI7 | Neighbourhood and Local Green Spaces | Provision of new open space, play areas, allotments and other local green infrastructure (and enhancements of existing) in line with the Green Space Supplementary Planning Guidance. To be specified in planning applications | 1 | 2000000 |  | 2000000 |  | 2000000 |  |  | *Being specified in planning applications - £140,000 for play equipment in Southern sites S106’S thus far | Early to medium 2017-2027
GI8 | Open Space Maintenance | Maintenance agreements to cover costs for 13 years. | 1 |  |  |  |  | 0 |  |  | *Normally calculated at point the open space is adopted using formula x 13 years | Early to medium 2017-2027
GI9 | Footpath connections | Enhance links in to countryside from new developments and beyond. To be specified in planning applications |  | 150000 |  | 150000 |  | 150000 |  |  | Public rights of way enhancement at the Asps
| Open Spaces Total |  |  | 5250000 | 3100000 | 2150000 | 0 | 5250000
Playing Pitches
GI10 | Football Pitches | Requirement for 5 additional full size pitches and 4 mini pitches across the District |  | 1590000 | 1200000 | 390000 |  | 1590000 |  |  | The Playing Pitch Strategy will be refreshed and an update provided in the Autumn of 2018 | Medium 2023-2027
GI11 | Cricket Pitches | Expansion of club infrastructure to increase adult cricket by 5 teams and 9 additional junior teams |  | 725000 | 650000 | 75000 |  | 725000 |  |  | The Playing Pitch Strategy will be refreshed and an update provided in the Autumn of 2018 | Medium 2023-2027
GI12 | Rugby Pitches | Expansion of club infrastructure to accommodate additional adult team, 3 additional junior teams and 3 additional midi team |  | 870000 | 750000 | 120000 |  | 870000 |  |  | The Playing Pitch Strategy will be refreshed and an update provided in the Autumn of 2018 | Medium 2023-2027
GI13 | Hockey Pitches | Additional demand for hockey by 5 teams, which could be accommodated on existing stock. However, the stock of artificial grass pitches will need renewing during the plan period. |  | 600000 | 550000 | 50000 |  | 600000 |  |  | The Playing Pitch Strategy will be refreshed and an update provided in the Autumn of 2018 | Medium 2023-2027
| Playing Pitches Total |  |  | 3785000 | 3150000 | 635000 | 0 | 3785000

## Open Spaces & Sports 2017-2022
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding
GI1 | Tach Brook Country Park | 62.5 hectare Country Park to north side of Tach Brook providing a separation and recreational space between Bishops Tachbrook and proposed new development to the south of Harbury Lane. Include pedestrian and cycle access, links to wider countryside, and ecological areas. Costs include maintenance and management for 13 years. | 1 | 2300000 | 0 | 2300000 | 0 | 2300000 | 0 | 0 | *£2,046,720 identified in Southern sites S106’s- the majority of the land required. Negotiations regarding Severn Trent land underway. Report due to November Executive regarding procurement of design consultant | Early 2017-2022
| Open Spaces & Sports Pitches 2017-2022 Total |  |  | 2300000 | 0 | 2300000 | 0 | 2300000 | 0 | 0

## Community Facilities & Monitori
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding
Community Facilities
CF1 | Warwick: Southern Sites Community Centre | New Community Centre, including 1 year start-up costs | 1 | 1200000 | 1200000 |  |  | 1200000 | 250000 |  |  | Early 2017-2022
CF1 | South of Harbury Lane Community Centre | New Community Centre, including 1 year start-up costs | 2 | 1200000 | 1200000 |  |  | 1200000 |  |  |  | Medium 2023-2027
CF2 | Kenilworth: Thickthorn Community Centre | New Community Centre, including 1 year start-up costs | 1 | 1200000 |  | 1200000 |  | 1200000 |  |  |  | Medium 2023-2027
CF3 | Kings Hill Community Centre / hall | New Community Centre, including 1 year start-up costs | 2 | 1200000 |  | 1200000 |  | 1200000 |  |  |  | Medium 2023-2027
Village Infrastructure
V1 | Village Infrastructure | The proposed housing allocations for the growth villages will require (over and above any educational requirements) associated infrastructure investments. For example this could include facilities for teenagers; sport and recreation facilities; improved community halls; allotments; nursery provision; local road improvements etc. | [5 empty] | 0 |  |  |  | TBC
| Community Facilities Total |  |  | 4800000 | 2400000 | 2400000 | 0 | 4800000 | 250000
Monitoring Fees
M1 | S106 and CIL Monitoring | Resource to manage and monitor Section.106 and CIL for10 years |  | 750000 |  | 750000 |  | 750000
| Monitoring Total |  |  | 750000 | 0 | 750000 | 0 | 750000

## Community Facil & Mon 2017-22
| Infrastructure Type / Project | Project Detail | Scheme Grading | Total Cost New Estimate | Estimate of Funding Type |  |  | Total CIL / s.106 / s.278 | Estimate of Other Funding |  | Update and Progress | Implementation Phase
[5 empty] | CIL | s.106 | s.278 |  | Other Committed Funding | Other Potential Funding
CF1 | Warwick: Southern Sites Community Centre | New Community Centre, including 1 year start-up costs | 1 | 1200000 | 1200000 | 0 | 0 | 1200000 | 250000 | 0 |  | Early 2017-2022
| Community Facilities & Monitoring 2017-2022 Total |  |  | 1200000 | 1200000 | 0 | 0 | 1200000 | 250000 | 0